## Checklist for Communication
Communication planning and budgeting checklist
The activities contained in this checklist (that are included in the campaign communication plan) should be included in the campaign's master timeline to ensure synchronization of communication activities with the roll out of the campaign and that communication activities and materials are ready for each phase of the campaign. This checklist should also serve as a basis for activities to be considered and then costed in the campaign budget for communication. The "Funding for what?" column should include as many details as possible for clarity during budget development and finalization. Who will fund and implement the activities will vary, and part of the planning phase will include assigning of roles and responsibilities and the formulation of realistic budgets for all activities. Some examples have been provided in the table, but the tool should be used and modified for each campaign by the communication subcommittee.
Steps for planning | Responsible | Funding required? | Funding for what? | Responsible | Notes | Further information and resources
Establish communication subcommittee and organize initial meetings
Carry out a mapping of malaria communication partners engaged in social mobilization and SBCC at community, district, regional and national levels |  | No |  | NMCP | Normally, the NMCP should have a list of all partners that are supporting malaria prevention and control activities, including those focused on local level communication.
Invite key partners and public health promotion/education representatives to participate in communication subcommittee. Carry out a mapping of local activities of partners (focus, scope, targeted households, districts, etc.) |  | No |  | NMCP | This is key and must be done early in the planning stage to ensure that all communication partners, as well as information, data and resources, are included in the development of messages and materials.
Communication subcommittee reviews and approves its terms of reference |  | Yes | Transport and per diem (where applicable); rental of venue; facilitation costs; stationery; etc. |  | Accomplished at first meeting of communication subcommittee and final terms of reference should be presented at next national coordination committee meeting for validation. | See accompanying narrative for example of terms of reference for communication subcommittee.
Communication subcommittee develops a timeline for key activities during the planning phase |  | Yes | Transport and per diem (where applicable); rental of venue; facilitation costs; stationery; etc. |  | Accomplished at first meeting of communication subcommittee and final timeline of subcommittee activities should be presented at next national coordination committee meeting for validation.
Organize partner workshop for strategy development
Convene a workshop with representatives of the different communication partners to: (1) Review existing research on net use, as well as on knowledge, attitude and practices regarding barriers and motivators to net use, care and repair; (2) Partners contribute their net use and care research findings; (3) Hone message segmentation, targeting along demographic, socio-economic and geographical lines; (4) Identify specific issues - such as sale of nets to market vendors or fishing - and specific target groups - such as adolescents; (5) Review reports and recommendations from previous campaign or continuous distributions and evaluations. |  | Yes | Rental of venue, coffee and lunch breaks; transport and per diem for participants; facilitation fees; workshop materials (such as flipchart paper, markers, etc.) |  | This workshop is a critical first step in the communication planning process, providing the opportunity to engage partners that have different expertise and knowledge about the different facilitators and barriers to uptake and use of malaria services. Often partners will have anecdotal or survey/research/project data that is unpublished but may be a rich source of information. | See Brief 3: Using research and data to plan effective social and behaviour change communication. See also two resources by Vector Works: www.vector-works.org/wp-content/uploads/PC.4.9-ITN-Misuse-for-Fishing-Toolkit-_FINAL.pdf and www.vector-works.org/resources/strategies-in-urban-distribution-of-insecticide-treated-nets/.
Undertake qualitative research to fill gaps in information
Where gaps in information are identified during the stakeholder workshop, it may be necessary to undertake focused qualitative research in specific areas or with specific population groups. Clearly define questions to be answered, methodology, who will undertake the field work and how information will be analysed. A protocol should be developed, as well as a timeline and budget to ensure that the research findings will be available in time to inform the campaign communication plan. |  | Yes | Hiring of organization to undertake and analyse data from qualitative research or, where this will be done by NMCP/NMEP and partner staff, costs for travel, accommodation and per diem, as well as organization of focus group discussions, should be budgeted. |  | It is important to ensure that there is sufficient time to collect, analyse and develop the recommendations for the campaign communication plan. Often, gaps in information are identified too late to take action prior to the campaign. Collection of communication data is important to ensure that messaging reflects the context and should be included in the National Strategic Plan and the associated budget as a routine activity.
Develop communication sections of campaign plan of action based on campaign strategy including:
Introduction to the campaign and the importance of social mobilization and SBCC for achieving campaign objectives. Summary of existing data and information regarding malaria and ITN knowledge, attitudes and perceptions, as well as any specific barriers identified, and how they have been used to formulate the campaign communication planning |  | No
Objectives of the communication plan in support of the campaign objectives (specific, measurable, achievable, realistic, time-focused) |  | No |  |  | Ensure alignment with objectives in the campaign plan of action.
Communication messaging at each phase of the campaign - Produce a set of technical and motivational messages for social mobilization and SBCC for the periods: prior to the household registration, during the household registration, prior to the ITN distribution, during the ITN distribution and post-distribution. Determine channels for dissemination of key messages, including radio, television, community and health facility workers, SMS messages, social media, etc. |  | Yes | Contracting of agency for development of creative brief (where necessary); pre-testing of materials with representative sample. |  | The development of communication messages must take into account rural and urban differences. The timeline must take into account the modifications that may be required after the pre-testing of the materials, as well as a second pre-testing if required. Plans for countering rumours and misinformation, as well as a strategy for responding to crisis situations or resistance to cooperation with the campaign should be considered. | How to develop a communication strategy (www.thecompassforsbc.org/how-to-guides/how-develop-communication-strategy).
Branding and production of campaign communication materials - The logo, slogan and song/jingle used for branding of NMCP/NMEP activities should be reviewed for compliance with the updated campaign messages. Where no branding is in place, an agency may be hired to develop the brand and supporting materials based on the creative brief. |  | Yes | Contracting of agency to produce all print, audio and visual materials; production of campaign communication materials; transport of campaign communication materials to implementation level. |  | Where the communication subcommittee does not have the technical resources required to develop the creative brief (which is used to instruct the creative agencies who will bid on designing a branding strategy and design of branded materials), it may be necessary to contract external support for this, which should be included in the budget. Tendering and contracting for production of materials must be included in the timeline based on the procedures for procurement (e.g. time for publication, review, selection and signature of contracts). | How to write a creative brief (www.thecompassforsbc.org/how-to-guides/how-write-creative-brief). Brief 5: Branding and promoting social norms.
Advocacy, engagement and outreach - Advocacy activities must be planned at all levels of the campaign. The communication plan should describe the role of key advocacy players, such as national malaria champions, and how they will contribute to achieving the campaign's objectives. Typically, advocacy meetings will take place at the national, regional and district levels with government agencies/ministries, representatives of religious and community groups and organizations, the private sector and others that are identified as key leaders and influencers. Additionally, community dialogue or village development committee meetings may be organized to ensure that all key actors at all levels are aware of the campaign and how it will be implemented. Advocacy packages should be developed that include fact sheets, frequently asked questions, talking points and key message. |  | Yes | Rental of venues, coffee and lunch breaks for advocacy meetings at national, regional, district levels; costs for participants (transport, per diem); materials for the meetings, including advocacy packages for participants, visibility materials, etc. Advocacy meetings may be organized in advance of the microplanning workshops, which represent the first steps towards implementation of the campaign. A budget should be included if there will be separate advocacy meetings around microplanning and then implementation. |  | Advocacy is important and meetings with leaders and influencers offer an opportunity to provide materials to explain actions/measures that can support the campaign. Telecom companies are often a specific target of advocacy to encourage them to participate through the dissemination of social mobilization and social behaviour change communication messages at each phase of the campaign. Remember to plan for advocacy with the Ministry of Fisheries, Environment, Agriculture, Migration, Mining, Refugees, etc. to collaborate on any barriers and issues related to key populations. The Ministry of Education may be an important stakeholder to promote school activities around household registration, ITN distribution and post distribution phases. Engagement with the private sector involves identifying the sectors and contributions in advance and specific tools may need to be prepared for the "pitch". | See: Brief 7: Advocacy events and materials. Brief 4: Private sector engagement.
Development and production of campaign communication and visibility materials - The communication plan must describe the materials that will be developed and reproduced for the campaign to ensure high awareness of the activities and visibility of campaign personnel. Materials may include posters, banners, t-shirts, aprons, caps and other supports as determined by the communication subcommittee. |  | Yes | Depends on materials. |  | The decisions around the materials that will be produced for the campaign communication and visibility must be taken early. This is a key source of campaign delays (late tendering, late contracting, late reception of materials and transport to implementation level, etc.)
Mass media engagement - The communication plan should include details about the planning for the use of broadcast media for each phase of campaign, including roles for centrally produced scripts and recorded materials as well as station produced programmes and announcements to allow an appropriate budget to be developed. It is important to organize media briefing or orientation sessions for radio and television professionals, as well as print media where this is an effective channel. The media briefing will be important at the central level, but may also be important at the regional and district levels, which should be accounted for in the communication plan and budget. |  | Yes | Printing of the media briefing kit and package of materials that will be provided to the media; media briefing sessions at national and other levels as appropriate (including rental of venue, coffee and lunch breaks [depending on duration], transport and per diem [as required] and facilitation costs; costs for dissemination of radio spots and programmes, as well as the participation of influencers and facilitators for all phases of activities. |  | Rural and urban areas should be differentiated in terms of mass media based on existing or new data. For example, radio may be an important channel in rural areas, while television and electronic media may be more effective channels in urban areas. Where cell phone access is high, a plan may be developed for SMS reminders in the post-distribution phase. Develop a standard curriculum and toolkit for the one-day orientation. | See Brief 8: Special requirements of social mobilization in urban areas. See also: www.vector-works.org/resources/strategies-in-urban-distribution-of-insecticide-treated-nets/.
National and sub-national campaign launch events - Often, the leader of a country or the Minister of Health will be asked to launch the ITN mass distribution campaign. The request must be made early and available resources identified. The country protocol should be followed in terms of invitees, ordering of interventions by participants, etc. A symbolic handover of ITNs to household members, demonstrating the way the ITNs will be received at distribution points (e.g. exchange of voucher or checking registration lists), is often organized. The key messages for the ITN distribution phase can be reiterated and reinforced by speakers. |  | Yes | Rental of venue, as well as sound system where not included; rental of generators and chairs and tables; reception event food and drinks; invitation cards; volunteers to help with seating arrangements; large banners for visibility; transport and per diem for participants and their drivers if needed; media coverage. |  | Campaign launch events are an important part of social mobilization and visibility of the campaign, but they are also expensive, particularly at the national level. The communication subcommittee should identify who is best to launch the campaign and then undertake early advocacy with the office responsible for ensuring this happens. At the decentralized levels, launch events are often organized at the district level. The budget for the launch event will depend on the protocol of each country, but it is important to not miss any important details.
Social mobilization - Activities to mobilize the household members in the targeted area are important and must be budgeted for at the macro planning stage. Social mobilization must take place prior to household registration, during household registration, prior to ITN distribution, during ITN distribution and post-distribution. The type and duration, as well as channels, for social mobilization will vary by country and, within countries, by urban, rural and other differences which need to be planned and budgeted for. |  | Yes | Depends on materials. |  | Social mobilization may include road shows, theatre, drama, sports events, house to house visits, inclusion of campaign messages in religious sermons, market walks, etc. The variety and type of channels for social mobilization should be determined early based on data where possible. In some cases, social mobilization activities may be organized in the period following the household registration to identify and register households that have not yet been reached. Where this is planned, it must be reflected in the budget, as well as the communication messages and timeline. | See Brief 9: Planning and implementing social mobilization and social and behaviour change communication.
SBCC during household registration, ITN distribution and post-distribution - The household registration and ITN activities offer important opportunities for interpersonal communication that must be capitalized on. During household registration, personnel must be trained on the key messages and frequently asked questions that may arise during the door-to-door visits and receive appropriate job aids to ensure messages are communicated in a consistent manner. During the ITN distribution, a health education area should be set up, demonstrating how a net should be hung and basing the demonstration on sleeping patterns in the area of the distribution point. |  | Yes | Printing of the job aids. |  | During all training sessions, people should practise with role plays and scenarios around different situations that may arise and questions that may be asked - personnel need to be prepared to respond. Ensure that job aids are available for the training for the household registration and ITN distribution and review the messages to ensure that they are clear. For the ITN distribution, consider putting the SBCC in the area where people are waiting to enter the distribution site - they are a captive audience versus when they have finally received their net. It is important to consider the post-distribution activities that may have the greatest reach at the time of the macro planning and budgeting. While these activities may not be prioritized at the time of the budgeting where there are financial shortfalls, if there are savings during the implementation they may be used to support the post-distribution communication.
Risk assessment and mitigation - the plan should describe some of the key risks related to communication and consider alternatives and mitigating strategies. Where a mitigating strategy may have a cost, this should be included in the budget during macroplanning to ensure flexibility during implementation if issues arise. |  |  | Depends on risks and mitigation measures. |  | The communication subcommittee should use the risk assessment and mitigation planning to discuss all possible risks (for example, political hijacking of the campaign if elections are close, rumours about the campaign or the nets, stock ruptures at distribution points, etc.) and identify how they can be mitigated. Careful risk planning will ensure that sufficient resources are budgeted to address anything that comes up.
Supervision and monitoring planning - this should include for training sessions, as well as determining the indicators that will be measured and the questions to be included on the supervision and monitoring tools for each phase of the campaign to gather data related to each indicator. |  | Yes | Costs for travel, per diem, accommodation for communication supervisors and monitors for the different phases of activity. |  | Supervisors and monitors must collect information on the frequency and quality of message dissemination.
Human resources for communication
Communication human resources required at each level of the health structure, as well as within other implementing partner organizations, and their roles and responsibilities during the campaign planning, implementation and post-distribution phases should be described in the communication plan. Any positions that require funding should be justified with a specific TOR and budget. |  |  | Depends on country. |  | Tendering, contracting and recruitment should be included in the timeline.
Communication microplanning
Develop or update communication microplanning tools, including the list of information to collect, the template that will be used to plan and budget for the activities, etc. |  |  | Depends on country. |  | Microplanning is as important for communication as for other campaign areas. It is important that the communication subcommittee modify existing or develop microplanning templates, with links to the associated budget, in advance of the TOT and workshops. The templates for microplanning should be developed on the basis of the communication plan. It is important that the SBCC experts who have developed the plan contribute to the list of information to be collected in advance of the microplanning workshops to ensure a comprehensive and funded communication approach adapted to the local context. | See Microplanning guidelines (allianceformalariaprevention.com/amp-tools/tools-resources/
Training of trainers for microplanning workshop roll out and ensuring that the communication microplanning is prioritized. |  | Yes | Travel, accommodation, per diem; facilitation costs. |  | National communication staff participation in the microplanning training of trainers to ensure that the importance of communication is not overlooked and that all individuals that will be facilitating microplanning training are aware of the communication template and how it should be filled out
Microplanning workshops and ensuring that the communication focal points from regional, district and health facility level are included. |  | Yes | Travel, accommodation, per diem; facilitation costs. |  | Regional/district communication staff participation in the microplanning workshops to ensure that communication aspects are included in the operational plan and budget for each district. Decisions should be taken about whether there is a need for communication representatives from the health facility/village level and, where this is a priority, the number of people and costs for their participation should be included.
Microplanning review, verification, consolidation and validation workshops and ensuring participation of communication focal points. |  | Yes | Travel, accommodation, per diem; facilitation costs. |  | Communication staff participate in the review, cleaning and validation of the microplans to ensure that communication activities are not reduced to generate savings.
Advocacy/engagement meetings in advance of microplanning workshops. |  | Yes | See above section on advocacy. |  | See above section on advocacy.
Training preparation and implementation
Input social mobilization and SBCC in training tools for central, regional and district level implementation trainings, including household registration and distribution point activities, as well as for post-distribution activities. |  | No |  |  | Ensure sufficient time is included in the agenda to cover communication activities and that SBCC is integrated into role-plays and group work. Key message job aids for use by campaign personnel during household registration and ITN distribution should be printed and available for training and implementation of activities. The costs for these should have been captured in the campaign communication and visibility materials. Where training evaluations/post-tests are used, ensure that questions on retention of key messages and communication channels and activities are included.
Training for implementation - Communication facilitators participate in all training of trainer sessions, as well as during supervision and monitoring of decentralized training sessions. |  | Yes | Travel, accommodation, per diem; facilitation costs. |  | The communication subcommittee should budget for these costs prior to verification that they have been captured in the overall campaign budget.
Supervision and monitoring of communication activities during each phase of the campaign
Communication staff at all levels (Ministry of Health and implementing partners) participate in supervision and monitoring, to ensure a specific focus on communication activities. |  | Yes | Travel, accommodation, per diem; facilitation costs |  | The communication subcommittee should budget for these costs prior to verification that they have been captured in the overall campaign budget.
Wrap-up and lessons learned
Post-distribution wrap-up meetings should be planned at all levels to gather information on successes and challenges and generate key lessons learned and recommendations for future campaigns. |  | Yes | Rental of venues at all levels; transport and per diem for facilitators and participants; facilitation costs; coffee breaks and lunches; stationery; etc. |  | It is critical that the communication activities receive sufficient focus during the wrap-up meetings. This will help to understand what worked and what did not work, as well as whether there are knowledge or behaviour gaps that need to be addressed prior to the next campaign. The communication subcommittee should budget for these costs prior to verification that they have been captured in the overall campaign budget.

## Checklist for SBCC Planning (2)
SBCC and Social Mobilization Planning and Budgeting Checklist
Steps | Responsible | Funding required? | Funding for what? | Notes | Responsible | Target for completion | Date completed | Further information
Establish Communication subcommittee
Carry out a mapping of local activities of malaria communication partners for planning sustained SBCC
Invite key partners and public health promotion/education representatives to participate in communication subcommittee. | [7 empty] | This is key and must be done early in the planning stage
Communication subcommittee reviews and approves its terms of reference |  |  |  | Accomplished at first meeting of communication subcommittee
Develop communication sections of campaign plan of action based on campaign strategy including: |  |  |  | A working group of the communication subcommittee takes responsibility for overseeing the drafting of its input into the campaign plan of action.
Summary of existing data and information regarding malaria and ITN knowledge, attitudes and perceptions, as well as any specific barriers identified, and how they have been used to formulate the campaign communication planning
Communication human resources at each level of the health structure, as well as within other implementing partner organizations, and their roles and responsibilities during the campaign planning, implementation and post-distribution phases
Communication in rural communities during each phase of the campaign
Communication in urban areas during each phase of the campaign
Post-distribution communication activities, including how supervision, monitoring, end process or other campaign data will be used to design the post-distribution communication campaign
Plans for countering rumors and disinformation, as well as a strategy for responding to crisis situations or resistance to cooperation with the campaign
The role of key advocacy players, such as national malaria champions, and how they will contribute to achieving the campaign's objectives
Microplanning
Develop or update communication microplanning tools, including the list of information to collect, the template that will be used to plan and budget for the activities, etc. The communication microplanning tool should be based on the communication plan, including plans for post-distribution communication
National SBCC staff participation in the microplanning training of trainers to ensure that the importance of communication is not overlooked and that all individuals that will be facilitating microplanning training are aware of the communication template and how it should be filled out
Regional / district SBCC staff participation in the microplanning workshops to ensure that communication aspects are included in the operational plan and budget for each district
Participation in the revew, cleaning and validation of the microplans to ensure that communication activities are not reduced to generate savings
Develop a message guide for each phase of the campaign
Review of existing research on net use, as well as on knowledge, attitude and practices regarding barriers and motivators to net use, care and repair. Review of reports and recommendations from previous campaign or continuous distributions and evaluations. |  |  |  | A consultant conducts a review of published and unpublished literature, and produces a study with findings.
Plan and conduct quick qualitative research to fill geographic or other gaps in understanding of knowledge, attitude and practices, if required. Clearly define questions to be answered, methodology, who will undertake the fied work and how information will be analyzed. |  |  |  | Based on review findings, identify funding and partners capable of conducting research to fill knowledge gaps to inform localized messaging.
Produce set of technical and motivational messages for BCC and social mobilization, including messages on social norm development, for the periods: prior to the household registration, during the household registration, prior to the ITN distribution, during the ITN distribution and post-distribution |  |  |  | Sub-committee members and key partners hold workshop to develop campaign message guide.
Determine channels for dissemination of key messages, including radio, television, community and health facility workers, SMS messages, etc.
Pretest messages with representative sampling |  |  |  | Organize focus groups to respond to key messages.
Revise messages/products if needed after pretesting |  |  |  | Meeting of communication sub-committee to respond to pre-testing findings.
Branding and production of campaign communication materials
Review existing / Develop logo and slogan and update to harmonize with current SBCC messaging | Subcommittee |  |  | This may involve contracting an external organization, which should be built into the timeline and budget early on.
Review existing / Develop malaria song for compliance with current messaging | Subcommittee |  |  | Designated working group of sub-committee review malaria song for its compatibility with goals of a universal campaign.
Produce creative brief that will instruct the creative agencies who will bid on designing a branding strategy and design of branded materials including printed materials, visibility materials (caps/aprons) and media spots | Subcommittee |  |  | May require external support
Open and review bids for production of communication materials. |  |  | Call for tenders, review of submissions, contracting fees, etc.
Produce visibility materials, media spots and printed materials
Mass Media
Establish plan for use of broadcast media for each phase of campaign, including roles for centrally produced scripts and recorded materials as well as station produced programs and announcements. |  |  |  | Include in the campaign Plan of Action.
Develop plan to mobilize broadcast media and SMS reminders following the receipt of nets by the beneficiaries with the goal of promoting net use, care and repair as well as repurposing of old and expired nets.
Determine budget for use of media outlets.
Develop a standard curriculum and a radio toolkit for a one-day orientation before each wave for radio professionals and health educators. |  |  |  | The communication sub-committee forms a training working group to assure that BCC and mobilization elements are incorporated into training curriculum and materials.
Develop a media monitoring tool to monitor mass media
Training
Input BCC and social mobilization communication in training tools for central, county and district level implementation trainings, including assessment and distribution site activities.
Include in training materials strategies for countering rumours and incidences in case of net shortages and rumors
Include ACSM guide for advocacy with county and district-level champions.
Design teaching aids for local-level training of CHWs in SBCC
Advocacy and outreach
The communication sub-committee forms an advocacy working group that will plan and supervise the implentation of advocacy activities.
Engagement meetings with Government, Ministries and other agencies, major stakeholders, private sector.
Elaborate a plan for advocacy meetings with diverse government agencies/ministries.
Elaborate a list of actions/measures in support of campaign that can be the basis of discussion with government agencies/ministries.
Prepare standard advocacy toolkit with fact sheets, frequently asked questions and talking points that can be adapted for each audience.
Calendarize advocacy meetings with government agencies, including parlamentarians.
Undertake advocacy for contributions from telecoms for free SMS reminders on net use.
Ministry of Education to promote school activities around HHA, distribution and post distribution phases.
Advocacy and Engagement with Non-Governmental Actors
Plan and conduct advocacy with national religious organizations.
Budget for agreed upon activities by national religious organizations.
Develop and execute a plan for private sector engagement.
Advocacy and engagement meetings at county level (including local media)
Plan for district advocacy meetings (sensitization) with local opinion makers, recognized religious leaders, leaders of community-based organizations and media to mobilize them as malaria champions in their district
Plan for follow-on community dialogs
National Launch |  |  |  | Identify roles and responsibilites for carrying out this activity.
Develop a plan for national launch activities, including media coverage.
Organize national launch event.
The activities contained in this checklist should be included in the campaign's master timeline to help ensure that implementation of communication activities is synchronized with the roll out of the campaign. This type of coordination is essential to assuring that all the communication outputs are ready for each phase of the campaign.
This checklist should also serve as a basis for activities that need to be costed in the campaign budget for SBCC. The "Funding for what?" column should include as many details as possible to ensure that things are not forgotten during budget development and finalization. Some examples have been provided.
Typically the campaign's communication subcommittee will oversee the activities, dividing into working groups to plan specific tasks.
Who actually will implement the activities will vary according to circumstances, and part of the planning will be assure the assignment of implementation responsibility and the formulation of realistic budgets for all activities.