**AMP Conference call m****inutes August 11th, 2021**

<https://allianceformalariaprevention.com/>

**To be added to the AMP mailing list please visit this page:** [https://allianceformalariaprevention.com/weekly-conference-call/signup-for-our-mailing-list/](https://ifrc.us7.list-manage.com/track/click?u=f9029b11cb24c24e0f54ae46d&id=23424f7aa5&e=c1f7a5c792)

Do you have a topic / issue / update to share with the AMP partnership? Please send a summary to [elisa.riquier@ifrc.org](mailto:elisa.riquier@ifrc.org) to schedule your update at the start of an upcoming AMP conference call.

**Agenda – August 11th AMP conference call**

Chair : Jason PEAT

Rapporteur :  Orianne BERRAUD

* + - Country updates
    - Working Group updates
    - AoB

**Number of participants August 11th call**

* 36 participants

Next conference call**: Wednesday August 18th, 10:00 EDT, 14:00 GMT / UTC, 16:00 CEST**

**I. GENERAL UPDATES**

1. **Topics of discussion for upcoming AMP conference calls**

|  |  |  |  |
| --- | --- | --- | --- |
| **Date of upcoming AMP conference call** | **Topic** | **Focal point & Agency** |  |
| August 18th | No focus topic | N/A |  |
| August 25th | No focus topic | N/A |  |
| September 1st | No focus topic | N/A |  |
| September 8th | No focus topic | N/A |  |

**I. COUNTRY UPDATES**

**Country updates provided on August 11th AMP call**

|  |
| --- |
| **Angola** |
| * The next campaign is planned in 2022 * Initial coordination meeting held - USAID PMI as implementing partner in-country * Initial call with World Vision where planning has been discussed. GF will cover 2 provinces and PMI 6 provinces * There is no global strategy document yet to guide the campaign * Two types of nets that are supposed to arrive end between Dec 2021 to Feb 2022 * Some concerns around Communications   No feedback received on the ToRs. Marcy to be in touch with PMI (implementing partner on the ground). Chris to facilitate the connexion. Perhaps a coordination call needs to be organized (GF, PMI, NMCP, key stakeholders). |

|  |
| --- |
| **Burkina Faso** |
| Macro plan for the campaign sent. Feedback sent back to country. Workshop to finalize postponed to the week of 24th of August. |

|  |  |  |
| --- | --- | --- |
| **Burundi** | | |
| Campaign summary table | Population at risk of malaria | Total population: 11 215 578 |
| Target population | 9 824 522 |
| Geographic reach of campaign | 41 health districts (47 HD in total in country) |
| Total number of ITNs | 6 386 020 |
| Type of ITNs | IG2, PBO ITN and standard LLIN – funded by GF |
| Date planned for microplanning | Not started |
| Date planned for HHR | Not started |
| Date planned for ITN distribution | June 2022 |
| Country summary | * Campaign strategy defined * ITNs have been procured * Digital tools or not - under discussion / not clearly defined etc * AMP TA in place through RBM * PPE procured | |
| Meeting update | * Continuation of the work of the thematic groups to complete the sections to be updated and finalize the descriptions; * Consolidation between thematic groups of the single document on lessons learned; * Update of the campaign timeline; * Participation in the weekly MPA call.   **Major challenges**   * Operationality/Coordination/responsiveness of committees and sub-committees; * Conduct of the multi-product strategy; * Communication adapted to the multi-product campaign and to the management of rumors and fears induced by the COVID-19 pandemic context; * Targeted communication for ROs not enrolled in the 2022 MDC; * Timely and correct payment of actors; * Increase in reported COVID-19 cases in the country. | |

|  |  |  |
| --- | --- | --- |
| **Cameroon** | | |
| Campaign summary table | Target population |  |
| Geographic reach of campaign | First phase = 3 regions (Adamaoua, Extreme-North and North), Feb 2022  2nd phase = 4 regions (East, Littoral, West and South), Sept 2022  3rd phase = 3 regions (Centre, North-West and South-West), October 2023 |
| Total number of ITNs | 16 756 141 (estimated) |
| Type of ITNs | IG2, PBO ITN and standard LLIN – funded by Government and GF |
| Date planned for microplanning | Not started |
| Date planned for HHR | Not started |
| Date planned for ITN distribution | 2022-23 |
| Country summary | * Campaign strategy under discussion * ITNs have been procured * Digital tools - under discussion / not clearly defined * AMP TA in place through RBM - started on 15/06/2021 * PPE not yet procured | |
| Meeting update | * Draft 1 of the plan of action available and being finalized; * Draft 1 of the logistics plan available and submitted to the back stopper before sharing with the NMCP; * Working on the timeline of the campaign * Meetings ongoing (SBC comms, WFP) * First phase: nets 5 700 000 ITN supposed to arrive between dec 2021 Jan 2022. * Second phase: 4 phase : 5 200 000 : between June – July 2022 * Third phase: three regions : 5 800 000 expected march and April 2023. * Risk to have IG2 ITN delivered late: discussion with NMCP coordination : working on a plan B in case the ITN are delayed. * Plans for risk analysis and mitigation : first draft ready to share by the end of this week. * NMCP and AMP agreed to push the activities on comms : Miko supporting the comms director to support the plan of action. | |

|  |  |  |
| --- | --- | --- |
| **CAR** | | |
| Campaign summary table | Target population | 2 305 488 (total population of 5 570 570) |
| Geographic reach of campaign | 07 Health Regions |
| Total number of ITNs | 1 410 371 + 1 193 550 PBO + 216 821 |
| Type of ITNs | PBO ITN – funded by GF |
| Date planned for microplanning | July 2021 |
| Date planned for HHR |  |
| Date planned for ITN distribution | ITN distribution will take place in September 2021 in Bangui (Health Region 7) / ITN distribution will take place in November / December in Health Regions 4-5-6 |
| Country summary | * Campaign strategy under discussion * ITNs have been procured * Digital tools - under discussion / not clearly defined * AMP TA in place through RBM * PPE not yet procured | |
| Meeting update | New TA request submitted - not all deliverables were delivered in the previous TA.  Delays due to the ongoing transition of the implementation from service providers to Health Ministry structures. | |

|  |  |  |
| --- | --- | --- |
| **Cote d’Ivoire** | | |
| Campaign summary table | Target population | 27 614 525 |
| Geographic reach of campaign | National |
| Total number of ITNs | 19 313 573 |
| Type of ITNs | PBO nets – funded by Government, GF and PMI |
| Date planned for microplanning | Complete |
| Date planned for HHR | Complete (March 15th – 25th 2021) |
| Date planned for ITN distribution | Complete May 2021 |
| Country summary | * Campaign complete * Awaiting final report from NMCP | |
| Meeting update | No update | |

|  |  |  |
| --- | --- | --- |
| **Congo Brazzaville** | | |
| Campaign summary table | Target population |  |
| Geographic reach of campaign |  |
| Total number of ITNs |  |
| Type of ITNs |  |
| Date planned for microplanning |  |
| Date planned for HHR |  |
| Date planned for ITN distribution |  |
| Country summary | * Added to the agenda as they are planning for the 2022 campaign | |
| Meeting update | * CRS contacted AMP. Country is planning for a distribution in July. 2022. * Objective is to have cleaned macro and micro plans by end of 2021/ early 2022 | |

|  |  |  |
| --- | --- | --- |
| **DRC** | | |
| Campaign summary table | Target population |  |
| Geographic reach of campaign | Three provinces: Tanga, Congo Central, Haut-Lomami` |
| Total number of ITNs | 39 143 869   * Distribution of 4 million ITNs completed in Haut Katanga Province * Distribution of 2.4 million ITNs in Haut-Lomami * Distribution of 2 million ITNs in Tanganyika * Distribution of 3.1 million ITNs in Congo Central * Distribution underway in the North East of the country - 1.2 million ITNs will be distributed in total (600,000 standard ITNs and 600,000 PBO) * Distribution of 3.6 million ITNs planned in Ituri Province |
| Type of ITNs | PBO ITN – funded by GF, PMI and AMF |
| Date planned for microplanning | Complete |
| Date planned for HHR | Complete |
| Date planned for ITN distribution | 2020-2021 |
| Country summary | * COVID-19 adapted strategy door-to-door * Simultaneous registration and distribution * Fully digitized campaign roll-out * ITNs procured * PPE procured | |
| Meeting update | No update | |

|  |  |  |
| --- | --- | --- |
| **Ethiopia** | | |
| Campaign summary table | Target population |  |
| Geographic reach of campaign | 11 districts |
| Total number of ITNs | 10 585 959 - funded by GF and PMI |
| Type of ITNs | Standard LLIN – funded by GF and PMI |
| Date planned for microplanning |  |
| Date planned for HHR |  |
| Date planned for ITN distribution | 2021-2022 |
| Country summary | * PMI funded ITNs to arrive in February * Remaining ITNs will arrive in April * Central level ToT and micro planning to take place next week * Workshops will cover lessons learned | |
| Meeting update | No update | |

|  |  |  |
| --- | --- | --- |
| **Ghana** | | |
| Campaign summary table | Target population |  |
| Geographic reach of campaign | 10 regions in two phases |
| Total number of ITNs | 16 225 716 |
| Type of ITNs | PBO ITN, standard LLIN and IG2 |
| Date planned for microplanning | Complete |
| Date planned for HHR | Phase 1 HHR complete  Phase 2 : HHR between June 2-8 |
| Date planned for ITN distribution | Distribution will take place between May 18th -24 2021 for phase 1 regions and in June 2021 for phase 2 regions |
| Country summary | * Two-phase household registration and distribution with NetApp * COVID-19 mitigation measures are masks and two foot spacing at the distribution points. there's also no coupons to be exchanged the net app will capture the phone numbers or ID numbers. distribution points will not be significantly increased just for population increases and the number of days of distribution in the urban areas are being increased * Planning a multi-product campaign in 2022 * PPE procured | |
| Meeting update | * Northern and Western regions are currently implementing campaigns. Processes are being completed and ITN to be received by mid-September * Training of registration assistants ongoing * HHR next week | |

|  |  |  |
| --- | --- | --- |
| **Kenya** | | |
| Campaign summary table | Total number of ITNs | 15 707 752 – funded by PMO and GF |
| Type of ITNs | Standard LLIN and PBO ITN |
| Country summary | * Two-phase household registration and distribution * COVID-19 mitigation measures are masks and two foot spacing at the distribution points * PPE procured | |
| Meeting update | No update | |

|  |  |  |
| --- | --- | --- |
| **Liberia** | | |
| Campaign summary table | Target population | 4,931,090 (2018 campaign microplan population projected to 2021 at a growth rate of 2.1 %) |
| Geographic reach of campaign | National, covering all 15 counties in Liberia |
| Total number of ITNs | 2,783,264 |
| Type of ITNs | IG2 - procured by GF |
| Date planned for microplanning | Complete |
| Date planned for HHR | Complete |
| Date planned for ITN distribution | June 2021 |
| Country summary | * Two-phase household registration and distribution for 14 rural counties fixed point distribution and 1 urban county door-to-door distribution * COVID-19 mitigation measures are masks and two foot spacing at the distribution points * Limited digital data collection from Kobo * AMP TA in place through RBM * PPE procured * New net type, Interceptor G2 to be distributed in all counties | |
| Meeting update | * TA provider contract ended * Working on closing the process and securing the remaining ITNs currently * Data reconciliation difficult to be completed due to the challenges faced during the campaign planning and distribution * Response to rumours have been integrated in the SBC response plan. Frequency of the rumours decreased | |

|  |  |  |
| --- | --- | --- |
| **Madagascar** | | |
| Campaign summary table | Target population | 22,395,517 |
| Geographic reach of campaign | 101 districts (114 districts in total in country) |
| Total number of ITNs | 10,719,800 MID Standards (GF) / 3,677, 000 MID Standards (PMI) / 277, 350 MID PBO (GF) |
| Type of ITNs | Standard LLIN and PBO ITN |
| Date planned for microplanning | May 2021 |
| Date planned for HHR | August 2021 |
| Date planned for ITN distribution | August 2021 |
| Country summary | Two-phase household registration and distribution at fixed points  Digital data collection happening  COVID-19 mitigation measures are masks and two foot spacing at the distribution points  PPE procured | |
| Meeting update | * HHR being finalized – almost 67 district submitted their data * However, data transmission from certain districts still to be released. The objective for the NMCP is to have the data transmitted by the end of this week * Net transportation at district level finalized * PPE enough to cover activities - they were mobilized locally through partners * Looking to do some work around digitization : a consultant will be hired under the BMGF funding to support this work – key to country   **Challenges :**   * Waste management due to the PPE: during the discussions, the country stated that it has guidelines for waste management, namely burial with landfill sites * Some of the districts which already transmitted their data showed a higher need of ITN than what was planned in the macro plan * AMP TA team agreed to continue to support country with ongoing challenges | |

|  |  |  |
| --- | --- | --- |
| **Malawi** | | |
| Campaign summary table | Target population | 16,665,561 |
| Scale of campaign | 25 districts out of 29 Malawi districts (4 IRS districts excluded) |
| Total number of ITNs | 9,258,645 |
| Breakdown of nets | 3,749,406 IG2  516,677 Royal Guard  4,992,562 PBO nets |
| Date planned for microplanning | May 2021 |
| Date planned for HHR | August 2021 |
| Date planned for ITN distribution | October/ November 2021 |
| Country summary | * Two-phased fixed site distribution strategy with a door-to-door household registration followed by fixed-site distribution three months later. They will use registration books to identify recipients at the distribution points * The 2021 mass ITNs distribution campaign will target 25 districts in Malawi. Excluded from the campaign are Mangochi, Balaka, Nkhotakota and Nkhata Bay districts that will benefit from the indoor residual spraying (IRS) program. * COVID-19 mitigation measures are masks and two foot spacing at the distribution points * A mop-up distribution is planned for two communities of Chauma and Lupachi in Nkhotakota district. These are hard-to-reach communities in an IRS district that were not reached during the IRS activity * The first batch of nets is planned to start being shipped on 20/07/2021 | |
| Meeting update | * All approval documents ready to be submitted | |

|  |  |  |
| --- | --- | --- |
| **Niger** | | |
| Campaign summary table | Target population | 7 708 784 |
| Geographic reach of campaign | 4 regions (Agadez, Tahoua, Maradi and Zinder) |
| Total number of ITNs | 4 411 138 |
| Type of ITNs | Standard LLIN – funded by GF |
| Date planned for microplanning | Complete |
| Date planned for HHR | Complete |
| Date planned for ITN distribution | Complete May-June 2021 |
| Country summary | * 2021 campaign complete * 2022 campaign will be implemented in 7 regions (9 424 727 ITNs planned) and involve the new net types | |
| Meeting update | No update | |

|  |  |  |
| --- | --- | --- |
| **Nigeria** | | |
| Campaign summary table | Target population |  |
| Geographic reach of campaign | 10 states (funded by USAID PMI and the GF) |
| Total number of ITNs | 28 210 129 in 2021 / 26 192 725 in 2022 / 33 622 816 in 2023 |
| Type of ITNs | Standard LLIN and PBO ITN |
| Date planned for microplanning | Complete |
| Date planned for HHR |  |
| Date planned for ITN distribution | July 2021 |
| Country summary | * 2 distribution strategies   + Global fund is the single-phase simultaneous registration door to door distribution   + PMI is two phase and distribution through fixed sites * Currently GF is digitized (Redrose) and PMI looking to digitized for future campaigns | |
| Meeting update | No update | |

|  |  |  |
| --- | --- | --- |
| **Pakistan** | | |
| Campaign summary table | Target population |  |
| Geographic reach of campaign | 3 provinces |
| Total number of ITNs | 3 998 484 |
| Type of ITNs | Standard LLIN |
| Date planned for microplanning |  |
| Date planned for HHR |  |
| Date planned for ITN distribution | ITN distribution completed on Dec. 3rd 2020  2021 TBD |
| Country summary | * Campaign Strategy not yet determined * Plans for digital data collection - Pakistan is looking at using Red rose for their hybrid strategy * Delays in campaign due to the quality issue for the Nets which are blocked while that's sorted out | |
| Meeting update | * A serie of meeting calls took place for discussing on the coordination, planning, and drafting of the campaign documents. As a result,   + Participated in the weekly meeting with the country’s 2021 ITN mass campaign coordination team (GF-CT, DOMC, IHN, IFRC/PCRS, AMP)   + Campaign plan of action has been drafted and undergoing final review before validation   + Logistics campaign plan of action is drafted and being reviewed by the logistics sub-committee   + The SBCC component of the campaign plan of action has been drafted after several discussions with Pakistan malaria team and other members of the SBCC sub-committee’ the draft of the annexes SBCC POA is near completion and consultations with the Pakistan SBCC subcommittee continue to finalize aspects of the plan   + Lessons learned from previous campaigns in 2019 and 2020 is drafted and is undergoing review for finalization   + Waste management plan documents have been drafted and being reviewed for finalization by the logistics sub-committee and other members of the Pakistan malaria team   + Discussion was made on the budget document, and it was decided to have a consolidated budget document for activities to be financed by both PRs (DoMC and IHHN). It was also decided and agreed that the budget document includes all activities planned in the POA including the activities to be done by the PRs (central level TOTs, M&E activities, and post distribution activities). This is expected to be done by DOMC and IHHN. * Covid situation in country will be discussed and (email sent to the PR in country) and national coordinator for the covid response. | |

|  |  |  |
| --- | --- | --- |
| **Uganda** | | |
| Campaign summary table | Target population |  |
| Geographic reach of campaign |  |
| Total number of ITNs | 13 000 000 |
| Type of ITNs |  |
| Date planned for ITN distribution | Complete |
| Country summary | * Campaign complete | |
| Meeting update | * No update | |

|  |  |  |
| --- | --- | --- |
| **Zambia** | | |
| Campaign summary table | Target population | 10,5 million |
| Geographic reach of campaign |  |
| Total number of ITNs | 5,7 million |
| Type of ITNs |  |
| Date planned for ITN distribution | Complete |
| Country summary | * Campaign complete * Misuse study planed in 2020 but postponed to COVID-19 (to assess the misuse of nets for fishing). Need to follow up on this. | |
| Meeting update | * No update | |

**II. WORKING GROUP UPDATES**

***Continuous distribution Working Group:***

Co-chairs: Janee Miller (PMI VectorLink Project) [jmiller@psi.org](mailto:jmiller@psi.org) & Balla Kandeh (NMCP The Gambia): *[ballakandeh@yahoo.co.uk](mailto:ballakandeh@yahoo.co.uk)*

* No update

***Country support Working Group:***

Chair: Marcy Erskine (IFRC) [marcy.erskine@ifrc.org](mailto:marcy.erskine@ifrc.org)

* No update

***Innovation and Evaluation Working Group:***

Co-chairs: Joe Lewinski (CRS) [joseph.lewinski@crs.org](mailto:joseph.lewinski@crs.org) & Jessica Rockwood (IPHA) [jrockwood@iphadvisors.com](mailto:jrockwood@iphadvisors.com)

* No update

***Net mapping project Working Group:***

Chair: John Milliner (Milliner Global Associates) [jemilliner@gmail.com](mailto:jemilliner@gmail.com)

* No update

***Multi-Product Working Group:***

Co-chairs: Chris Lourenco (PSI) clourenco@psi.org & Miko Thomas mikojthomas@gmail.com

* Documents being finalized

***Resource Mobilization Working Group:***

Co-chairs: David Gittelman (DMG Global) [david@dmgglobalhealth.com](mailto:david@dmgglobalhealth.com) & Jason Peat (IFRC) [Jason.peat@ifrc.org](mailto:Jason.peat@ifrc.org) & Jessica Rockwood (IPHA) [jrockwood@iphadvisors.com](mailto:jrockwood@iphadvisors.com) & Drake Zimmerman (Rotarians Action Group on Malaria) [drakezim@gmail.com](mailto:drakezim@gmail.com)

* No update

***Toolkit and Training Working Group:***

Chair: Marcy Erskine (IFRC) [marcy.erskine@ifrc.org](mailto:marcy.erskine@ifrc.org)

* No update