**AMP Conference call m****inutes August 18th, 2021**

<https://allianceformalariaprevention.com/>

**To be added to the AMP mailing list please visit this page:** [https://allianceformalariaprevention.com/weekly-conference-call/signup-for-our-mailing-list/](https://ifrc.us7.list-manage.com/track/click?u=f9029b11cb24c24e0f54ae46d&id=23424f7aa5&e=c1f7a5c792)

Do you have a topic / issue / update to share with the AMP partnership? Please send a summary to elisa.riquier@ifrc.org to schedule your update at the start of an upcoming AMP conference call.

**Agenda – August 18th AMP conference call**

Chair : Jason PEAT

Rapporteur :  Orianne BERRAUD

* + - Country updates
		- Working Group updates
		- AoB

**Number of participants August 18th call**

* 35 participants

Next conference call**: Wednesday August 18th, 10:00 EDT, 14:00 GMT / UTC, 16:00 CEST**

**I. GENERAL UPDATES**

1. **Topics of discussion for upcoming AMP conference calls**

|  |  |  |  |
| --- | --- | --- | --- |
| **Date of upcoming AMP conference call** | **Topic** | **Focal point & Agency** |   |
| August 25th  | No focus topic | N/A |  |
| September 1st  | No focus topic | N/A |  |
| September 8th  | No focus topic | N/A |  |
| September 15th  | No focus topic | N/A |  |

**I. COUNTRY UPDATES**

**Country updates provided on August 18th AMP call**

|  |
| --- |
| **Angola** |
| * The next campaign is planned in 2022
* Initial coordination meeting held - USAID PMI as implementing partner in-country
* Initial call with World Vision where planning has been discussed. GF will cover 2 provinces and PMI 6 provinces
* There is no global strategy document yet to guide the campaign
* Two types of nets that are supposed to arrive end between Dec 2021 to Feb 2022
* Some concerns around Communications
 |

|  |
| --- |
| **Burkina Faso** |
| * TA ToR sent to the NMCP
* Workshop planned on 24-28 August to review the campaign implementation plan. Two subjects will be discussed in detail during that meeting.
	+ Digitization at one time, pilot phase first and then all country?
	+ IT technicians: should they employ external staff or assign the district IM managers?
* Macro plan : feedback will be sent by Marcy to the country team
 |

|  |
| --- |
| **Burundi** |
| Campaign summary table | Population at risk of malaria  | Total population: 11 215 578 |
| Target population | 9 824 522 |
| Geographic reach of campaign | 41 health districts (47 HD in total in country) |
| Total number of ITNs | 6 386 020 |
| Type of ITNs | IG2, PBO ITN and standard LLIN – funded by GF |
| Date planned for microplanning | Not started  |
| Date planned for HHR | Not started |
| Date planned for ITN distribution | June 2022 |
| Country summary | * Campaign strategy defined
* ITNs have been procured
* Digital tools or not - under discussion / not clearly defined etc
* AMP TA in place through RBM
* PPE procured
 |
| Meeting update | **Overall status of campaign planning and implementation*** Continued work on the communication plan collateral documents (rumor management plan, advocacy strategy, and communication training module)
* Reviewing/finalizing/formatting the drafts as they stand (timeline; action plans; tools and materials for training, logistical tracking, performance monitoring and for microplanning) while awaiting feedback and additions from the NMCP
* Preparation of the end of mission report for the implementation, monitoring-evaluation and logistics components of the remote TA
* End of the remote TA for the implementation, monitoring-evaluation and logistics components on August 15, 2021; SBC activities will be ongoing until the end of August

**Major Challenges*** Operationality/Coordination/responsiveness of committees or even subcommittees
* Conducting the multi-product strategy
* Communication adapted to the multi-product campaign and to the management of rumors and fears induced by the COVID-19 pandemic context
* Targeted communication for health districts not enrolled in the 2022 mass distribution campaign
* Timely and correct payment of actors
* Increase in reported COVID-19 cases in the country
* Meeting with the GF country team to discuss the availability of the program to work with AMP.
 |

|  |
| --- |
| **Cameroon** |
| Campaign summary table | Target population |  |
| Geographic reach of campaign | First phase = 3 regions (Adamaoua, Extreme-North and North), Feb 20222nd phase = 4 regions (East, Littoral, West and South), Sept 20223rd phase = 3 regions (Centre, North-West and South-West), October 2023 |
| Total number of ITNs | 16 756 141 (estimated) |
| Type of ITNs | IG2, PBO ITN and standard LLIN – funded by Government and GF |
| Date planned for microplanning | Not started |
| Date planned for HHR | Not started |
| Date planned for ITN distribution | 2022-23 |
| Country summary | * Campaign strategy under discussion
* ITNs have been procured
* Digital tools - under discussion / not clearly defined
* AMP TA in place through RBM - started on 15/06/2021
* PPE not yet procured
 |
| Meeting update | * No update
* The preparation meeting for the national coordination committee meeting with NMCP is postponed to next week
 |

|  |
| --- |
| **CAR** |
| Campaign summary table | Target population | 2 305 488 (total population of 5 570 570) |
| Geographic reach of campaign | 07 Health Regions |
| Total number of ITNs | 1 410 371 + 1 193 550 PBO + 216 821 |
| Type of ITNs | PBO ITN – funded by GF |
| Date planned for microplanning | July 2021 |
| Date planned for HHR |  |
| Date planned for ITN distribution | ITN distribution will take place in September 2021 in Bangui (Health Region 7) / ITN distribution will take place in November / December in Health Regions 4-5-6 |
| Country summary | * Campaign strategy under discussion
* ITNs have been procured
* Digital tools - under discussion / not clearly defined
* AMP TA in place through RBM
* PPE not yet procured
 |
| Meeting update | No update |

|  |
| --- |
| **Cote d’Ivoire** |
| Campaign summary table | Target population | 27 614 525 |
| Geographic reach of campaign | National |
| Total number of ITNs | 19 313 573 |
| Type of ITNs | PBO nets – funded by Government, GF and PMI |
| Date planned for microplanning | Complete |
| Date planned for HHR | Complete (March 15th – 25th 2021) |
| Date planned for ITN distribution | Complete May 2021 |
| Country summary | * Campaign complete
* Awaiting final report from NMCP
 |
| Meeting update | No update |

|  |
| --- |
| **Congo Brazzaville** |
| Campaign summary table | Target population |  |
| Geographic reach of campaign |  |
| Total number of ITNs |  |
| Type of ITNs |  |
| Date planned for microplanning |  |
| Date planned for HHR |  |
| Date planned for ITN distribution |  |
| Country summary | * Added to the agenda as they are planning for the 2022 campaign
 |
| Meeting update | No update  |

|  |
| --- |
| **DRC** |
| Campaign summary table | Target population |  |
| Geographic reach of campaign | Three provinces: Tanga, Congo Central, Haut-Lomami` |
| Total number of ITNs | 39 143 869* Distribution of 4 million ITNs completed in Haut Katanga Province
* Distribution of 2.4 million ITNs in Haut-Lomami
* Distribution of 2 million ITNs in Tanganyika
* Distribution of 3.1 million ITNs in Congo Central
* Distribution underway in the North East of the country - 1.2 million ITNs will be distributed in total (600,000 standard ITNs and 600,000 PBO)
* Distribution of 3.6 million ITNs planned in Ituri Province
 |
| Type of ITNs | PBO ITN – funded by GF, PMI and AMF |
| Date planned for microplanning | Complete |
| Date planned for HHR | Complete |
| Date planned for ITN distribution | 2020-2021 |
| Country summary | * COVID-19 adapted strategy door-to-door
* Simultaneous registration and distribution
* Fully digitized campaign roll-out
* ITNs procured
* PPE procured
 |
| Meeting update | * Maniema and Bas Uele provinces are finalizing the campaign
* Level of violence decreased in Ituri
 |

|  |
| --- |
| **Ethiopia** |
| Campaign summary table | Target population |  |
| Geographic reach of campaign | 11 districts |
| Total number of ITNs | 10 585 959 - funded by GF and PMI |
| Type of ITNs | Standard LLIN – funded by GF and PMI |
| Date planned for microplanning |  |
| Date planned for HHR |  |
| Date planned for ITN distribution | 2021-2022 |
| Country summary | * PMI funded ITNs to arrive in February
* Remaining ITNs will arrive in April
* Central level ToT and micro planning to take place next week
* Workshops will cover lessons learned
 |
| Meeting update | No update |

|  |
| --- |
| **Ghana** |
| Campaign summary table | Target population |  |
| Geographic reach of campaign | 10 regions in two phases |
| Total number of ITNs | 16 225 716 |
| Type of ITNs | PBO ITN, standard LLIN and IG2 |
| Date planned for microplanning | Complete |
| Date planned for HHR | Phase 1 HHR completePhase 2 : HHR between June 2-8 |
| Date planned for ITN distribution | Distribution will take place between May 18th -24 2021 for phase 1 regions and in June 2021 for phase 2 regions |
| Country summary | * Two-phase household registration and distribution with NetApp
* COVID-19 mitigation measures are masks and two foot spacing at the distribution points. there's also no coupons to be exchanged the net app will capture the phone numbers or ID numbers. distribution points will not be significantly increased just for population increases and the number of days of distribution in the urban areas are being increased
* Planning a multi-product campaign in 2022
* PPE procured
 |
| Meeting update | * HHR started on Monday 16th of August – expected to finish on Sunday 22nd in the Northern region. Progressing steadily, however, some communities HH are not present for registration as they are going out early for fieldwork.
* Distribution is expected 1between 3-19 September
 |

|  |
| --- |
| **Kenya** |
| Campaign summary table | Total number of ITNs | 15 707 752 – funded by PMO and GF |
| Type of ITNs | Standard LLIN and PBO ITN |
| Country summary | * Two-phase household registration and distribution
* COVID-19 mitigation measures are masks and two foot spacing at the distribution points
* PPE procured
 |
| Meeting update | No update |

|  |
| --- |
| **Liberia** |
| Campaign summary table | Target population | 4,931,090 (2018 campaign microplan population projected to 2021 at a growth rate of 2.1 %) |
| Geographic reach of campaign | National, covering all 15 counties in Liberia |
| Total number of ITNs | 2,783,264 |
| Type of ITNs | IG2 - procured by GF |
| Date planned for microplanning | Complete |
| Date planned for HHR | Complete |
| Date planned for ITN distribution | June 2021 |
| Country summary | * Two-phase household registration and distribution for 14 rural counties fixed point distribution and 1 urban county door-to-door distribution
* COVID-19 mitigation measures are masks and two foot spacing at the distribution points
* Limited digital data collection from Kobo
* AMP TA in place through RBM
* PPE procured
* New net type, Interceptor G2 to be distributed in all counties
 |
| Meeting update | * Each of the service provider presenting what has been done with HHR, distribution etc.
* Pressure to finalize for the lesson learned and review meeting.
* Draft agenda sent to the NMCP but no feedback received.
 |

|  |
| --- |
| **Madagascar** |
| Campaign summary table | Target population | 22,395,517 |
| Geographic reach of campaign | 101 districts (114 districts in total in country) |
| Total number of ITNs | 10,719,800 MID Standards (GF) / 3,677, 000 MID Standards (PMI) / 277, 350 MID PBO (GF) |
| Type of ITNs | Standard LLIN and PBO ITN |
| Date planned for microplanning | May 2021 |
| Date planned for HHR | August 2021 |
| Date planned for ITN distribution | August 2021 |
| Country summary | Two-phase household registration and distribution at fixed pointsDigital data collection happeningCOVID-19 mitigation measures are masks and two foot spacing at the distribution pointsPPE procured |
| Meeting update | * NMCP meeting :HH data transmission discussed : ITN need is higher than what was planned during the micro planification.
* 3,5 millions of mask as PPE
* HHR data base will be sent
 |

|  |
| --- |
| **Malawi** |
| Campaign summary table | Target population | 16,665,561 |
| Scale of campaign | 25 districts out of 29 Malawi districts (4 IRS districts excluded) |
| Total number of ITNs | 9,258,645 |
| Breakdown of nets | 3,749,406 IG2516,677 Royal Guard4,992,562 PBO nets |
| Date planned for microplanning | May 2021 |
| Date planned for HHR | August 2021 |
| Date planned for ITN distribution | October/ November 2021 |
| Country summary | * Two-phased fixed site distribution strategy with a door-to-door household registration followed by fixed-site distribution three months later. They will use registration books to identify recipients at the distribution points
* The 2021 mass ITNs distribution campaign will target 25 districts in Malawi. Excluded from the campaign are Mangochi, Balaka, Nkhotakota and Nkhata Bay districts that will benefit from the indoor residual spraying (IRS) program.
* COVID-19 mitigation measures are masks and two foot spacing at the distribution points
* A mop-up distribution is planned for two communities of Chauma and Lupachi in Nkhotakota district. These are hard-to-reach communities in an IRS district that were not reached during the IRS activity
* The first batch of nets is planned to start being shipped on 20/07/2021
 |
| Meeting update | No update |

|  |
| --- |
| **Niger** |
| Campaign summary table | Target population | 7 708 784 |
| Geographic reach of campaign | 4 regions (Agadez, Tahoua, Maradi and Zinder) |
| Total number of ITNs | 4 411 138 |
| Type of ITNs | Standard LLIN – funded by GF |
| Date planned for microplanning | Complete |
| Date planned for HHR | Complete |
| Date planned for ITN distribution | Complete May-June 2021 |
| Country summary | * 2021 campaign complete
* 2022 campaign will be implemented in 7 regions (9 424 727 ITNs planned) and involve the new net types
 |
| Meeting update | No update |

|  |
| --- |
| **Nigeria** |
| Campaign summary table | Target population |  |
| Geographic reach of campaign | 10 states (funded by USAID PMI and the GF) |
| Total number of ITNs | 28 210 129 in 2021 / 26 192 725 in 2022 / 33 622 816 in 2023 |
| Type of ITNs | Standard LLIN and PBO ITN |
| Date planned for microplanning | Complete |
| Date planned for HHR |  |
| Date planned for ITN distribution | July 2021 |
| Country summary | * 2 distribution strategies
	+ Global fund is the single-phase simultaneous registration door to door distribution
	+ PMI is two phase and distribution through fixed sites
* Currently GF is digitized (Redrose) and PMI looking to digitized for future campaigns
 |
| Meeting update | No update |

|  |
| --- |
| **Pakistan** |
| Campaign summary table | Target population |  |
| Geographic reach of campaign | 3 provinces |
| Total number of ITNs | 3 998 484 |
| Type of ITNs | Standard LLIN |
| Date planned for microplanning |  |
| Date planned for HHR |  |
| Date planned for ITN distribution | ITN distribution completed on Dec. 3rd 20202021 TBD |
| Country summary | * Campaign Strategy not yet determined
* Plans for digital data collection - Pakistan is looking at using Red rose for their hybrid strategy
* Delays in campaign due to the quality issue for the Nets which are blocked while that's sorted out
 |
| Meeting update | * Support ended last week. Currently working with campaign subcommittees (logistic and SBC). Supported the county to define campaign strategy for distribution of nets. Overall plan of campaign submitted and micro budget document drafted (still work in progress)
* Mitigation plan developed
* Key components of the SBC strategy is incorporated into the Plan of Action
* Comprehensive SBC Plan of Action submitted for review
* Rumour management plan submitted for validation
* Tracking tools and waste management plans developed and submitted for validation
* Covid situation and precautionary measures have been taken by the Covid Task Force including that the campaign is postponed to Q1 2022
* Delayed draft of the TA provider ToR sent back to the country
* Focus and follow-up to do concerning the arrival of afghan refugees crossing the border and settling in malaria endemic regions. Monitor the number of beneficiaries / ITNs needs as this will impact the planning and campaign coverage
 |

|  |
| --- |
| **Uganda** |
| Campaign summary table | Target population |  |
| Geographic reach of campaign |  |
| Total number of ITNs | 13 000 000 |
| Type of ITNs |  |
| Date planned for ITN distribution | Complete |
| Country summary | * Campaign complete
 |
| Meeting update | No update |

|  |
| --- |
| **Zambia** |
| Campaign summary table | Target population | 10,5 million |
| Geographic reach of campaign |  |
| Total number of ITNs | 5,7 million |
| Type of ITNs |  |
| Date planned for ITN distribution | Complete |
| Country summary | * Campaign complete
* Misuse study planed in 2020 but postponed to COVID-19 (to assess the misuse of nets for fishing). Need to follow up on this.
 |
| Meeting update | * No update
* Case study of the use of grid 3 : slide deck to be put together and to be shared with the AMP group. Discussion to be pursued with PMI
 |

**II. WORKING GROUP UPDATES**

***Continuous distribution Working Group:***

Co-chairs: Janee Miller (PMI VectorLink Project) jmiller@psi.org & Balla Kandeh (NMCP The Gambia): *ballakandeh@yahoo.co.uk*

* No update

***Country support Working Group:***

Chair: Marcy Erskine (IFRC) marcy.erskine@ifrc.org

* No update

***Innovation and Evaluation Working Group:***

Co-chairs: Joe Lewinski (CRS) joseph.lewinski@crs.org & Jessica Rockwood (IPHA) jrockwood@iphadvisors.com

* The waste management presentation will be updated by the 2nd week of September.
* Organize a call about waste management issues across all working groups

***Net mapping project Working Group:***

Chair: John Milliner (Milliner Global Associates) jemilliner@gmail.com

* Working group currently working on case studies and other guidance related to the new nets projects and multi products.

***Multi-Product Working Group:***

Co-chairs: Chris Lourenco (PSI) clourenco@psi.org & Miko Thomas mikojthomas@gmail.com

* Documents being finalized

***Resource Mobilization Working Group:***

Co-chairs: David Gittelman (DMG Global) david@dmgglobalhealth.com & Jason Peat (IFRC) Jason.peat@ifrc.org & Jessica Rockwood (IPHA) jrockwood@iphadvisors.com & Drake Zimmerman (Rotarians Action Group on Malaria) drakezim@gmail.com

* No update

***Toolkit and Training Working Group:***

Chair: Marcy Erskine (IFRC) marcy.erskine@ifrc.org

* No update

***Other updates***

Next core group call will be scheduled the 30th of August; discussion planned with RBM about challenges moving TA.