## Planning & budgeting checklist
Digital tools planning and budgeting checklist for ITN mass campaigns
The activities contained in this checklist should be included in the campaign's timeline to ensure that there are no delays related to the digitalization of the campaign. This checklist should also serve as a basis for activities to be considered and then costed in the campaign macro budget. The "Funding for what?" column should include as many details as possible for clarity during budget development and finalization. Who will fund and implement the activities may vary, and part of the digitalization macroplanning will include assigning roles and responsibilities to the national malaria programme and partners. The checklist may also identify gaps where resource mobilization is needed.
Steps for planning | Responsible | When? (timeline) | Funding required? | Funding for what? | Responsible | Notes | Further information and resources | Tick when completed
Establish digitalization sub-committee
Identify and Invite key partners from relevant departments, agencies and partner organizations to participate in sub-committee |  | Minimum of 12 months before distribution | No |  | National malaria programme (NMP) | The NMP (in consultation with MoH or other relevant government department) should develop a list of all agencies, departments and partners that are using digitalization. This is a critical step that must be done early in the planning process to ensure that all partners are informed, that they attend planned meetings and that their expertise and experience are capitalized on.
Organize an initial meeting to discuss the objectives and terms of reference (ToR) of the sub-committee, frequency of meetings and the need for additional technical teams and/or expert consultants (these needs may vary based on experience) |  |  | Yes | Transport and per diem (where applicable); rental of venue; facilitation costs; stationery; etc. Technical experts (internal or external) as needed | NMP | Draft ToR of digitalization sub-committee and any additional draft TORs for technical experts should be available for review and will need to be finalized subsequent to the meeting. NMPs with considerable experience in digitalization may decide to have an ICT4D technical team that reports directly to the National Coordination Committee and where this is the case, TOR should be developed for the ICT4D team.
The digitalization sub-committee establishes a timeline for key activities during the planning phase |  |  | No |  | Digitalization sub-committee | Example of key activities: mapping of apps and platforms in use within the MoH, operational needs analysis, context and digital landscape analysis, network access and company mapping, etc.
The digitalization sub-committee finalizes its ToR and develops additional ToRs for any required technical teams or experts for validation by the National Coordination Committee (NCC) |  |  | Yes | Human resource requirements such as technical teams or experts, etc. | Digitalization sub-committee | The context analysis will help to identify any technical expert needs required. For example, if lack of dedicated human resources had a negative impact on previous digitalization, then the NMP may want to increase the number of dedicated technical staff members. Question 8a. of the Context analysis also assesses the level of dedicated technical staff available.
The NCC approves the ToR of the digitalization sub-committee and the proposed additional technical experts (such as the ICT4D team or consultants) |  |  | Yes | Human resource requirements such as technical teams or experts, etc. | NMP/NCC | Consider seconding staff from other MoH departments when and if feasible (e.g. Health Information System staff).
Recruit/mobilize ICT4D team
Mobilize/recruit technical experts (such as members of the ICT4D team or external consultants) as per the decisions taken by the NCC and the policies/protocols of the funding or national malaria programme partners |  | 10 to 12 months before distribution | Yes / No | Funding may be required for (1) recruitment process, (2) staff members or consultants that need to be recruited | NMP | Even if the NMP or implementing partners have an existing ICT4D team or department, additional persons may need to be recruited to meet with the demands of the scope and scale of the ITN campaign. Existing ICT4D team members can begin processes of digitalization (such as the development of digitalization strategy/plan of action) while the recruitment is ongoing. Recruitment may be in a staggered approach, with the human resources required at central level recruited first to support planning, and human resources required at field level recruited just prior to implementation.
Organize meetings for strategy development
Convene digitalization sub-committee meeting to: (1) Review the campaign components and the possible challenges; (2) Revisit the "digitalization decision matrix" and make any adjustments necessary, 3) Identify the objectives for digitalization, (4) Identify the different digital platforms that can meet these objectives; (5) Discuss the pros and cons/limitations of each of the tools; (6) Decide which campaign activities should be digitalized |  | 10 to 12 months before distribution | Yes | Rental of venue, coffee and lunch breaks; transport and per diem for participants; facilitation fees; workshop materials (such as flipchart paper, markers, etc.). 3 to 5 days meeting. | NMP/Digitalization sub-committee/ICT4D team | This workshop is a critical first step in the digitalization process. It provides the opportunity to revisit the digitalization decision-making matrix with ICT4D technical experts or, where the digitalization decision-making matrix has not yet been completed, the workshop provides the time and space to ensure all areas have been considered. Often the ICT4D experts will be able to identify challenges, issues, opportunities and assets that non technical persons may have missed. The digitalization subcommittee and the ICT4D team should carry out a detailed context analysis to understand the operating environment (including challenges) at all levels. The context analysis can be similar to the context analysis in this decision matrix, but the assessment will be more detailed and ICT focused. Digitalization usually affects all thematic areas, so it is critical that other sub-committees (e.g. logistics, M&E) are represented during meetings with the ICT4D team, particularly when key decisions will be taken.
Recommendation of digital platform
Based on the operational needs, context analysis and in-depth ICT analysis, the ICT4D team can propose the digital platform (and associated tools and materials) to adopt for the campaign and present to the digitalization sub-committee for approval |  | 10 to 12 months before distribution | Yes / No | The tasks identified are part of the ICT4D team's TOR, but funds may be required for a workshop for these meetings (cost of venue rental, transportation, refreshment and lunch breaks, etc.) | ICT4D team | Take note of whether digital platforms have been used in the past and the extent to which they met expectations (refer to question 4 to 7 in the context analysis).
The digitalization sub-committee convenes a meeting to review and approve the recommendations of the ICT4D team, then tasks the ICT4D team to develop a strategy with detailed timelines and budget for the transition to digital platform |  |  | Yes / No |  | NMP/ICT4D team |  | Refer to The use of digital tools to improve operational efficiency guidance, and other digitalization documents on the AMP website: https://allianceformalariaprevention.com/tools-guidance/improving-itn-campaign-efficiency-through-use-of-digital-tools/
Develop a digitalization plan of action, including quantification, timeline, budget and risk assessment and mitigation
The digitalization sub-committee and ICT4D team develop a detailed digitalization plan of action (DPoA) describing the different components of the strategy, roles and responsibilities of different actors and training and support requirements for deployment of the system; the DPoA should include quantification, a timeline, a budget and a risk assessment and mitigation plan in annex to the document |  | 8 to 10 months before distribution | Yes / No | The development of the DPoA is part of the digitalization sub-committee's and ICT4D team's TORs, but funds may be required for a workshop for meetings (cost of venue rental, transportation, refreshment and lunch breaks, etc.) | Digitalization sub-committee/ICT4D team | Use the "Digitalization Plan of Action (DPoA)" template to help develop the plan of action.
Ensure familiarity with national rules, regulations, policies and procedures for collection of personal data and that a plan for data security is in place; make sure that these are reflected in the DPoA |  | 8 to 10 months before distribution | No | The development of the DPoA is part of the digitalization sub-committee's and ICT4D team's TORs, but funds may be required for a workshop for meetings (cost of venue rental, transportation, refreshment and lunch breaks, etc.) | NMP | There may be national rules, regulations, policies and procedures for the collection, storage and transmission of personal data. National malaria programmes should ensure that they are in conformity with national requirements. In addition, a breach of the database can be a high risk with negative consequences, so the national malaria programme needs to work with relevant government departments to develop plans to ensure the security of primary data collected during the campaign. This should be included in the risk assessment and mitigation plans.
Decide whether a pilot implementation is needed in advance of deploying the system at a larger geographic scale; describe the plans, area and timing for the pilot in the DPoA |  | 8 to 10 months before distribution | No | The development of the DPoA is part of the digitalization sub-committee's and ICT4D team's TORs, but funds may be required for a workshop for meetings (cost of venue rental, transportation, refreshment and lunch breaks, etc.) | Digitalization sub-committee/ICT4D team | Depending on previous experiences with large-scale digitalization of health activities, it may be necessary to pilot the system in a smaller geographic area to assess how it works, identify common challenges and put in place plans for mitigating any issues arising prior to the full deployment of the system. Ensure that any pilot of the system is done in areas with different contexts (e.g. best case scenario and worst case scenario).
Procurement, storage and transport
Undertake an inventory of equipment and materials for digitalization (e.g. computers, WiFi and MiFi, smartphones or tablets, power banks, etc.), including quantity, location and condition; finalize quantification for procurement based on needs versus existing equipment and materials |  | 8 to 10 months before distribution | Yes / No |  | NMP and digitalization sub-committee | If the context analysis shows that several programmes within the NMP and MoH are being digitalized, then there is a good chance that some of the devices and other tools required already exist and do not need to be procured.
Launch tender process for procurement of digitalization equipment and materials required as per macroquantification; centralize existing digitalization materials where these already exist |  |  | Yes | Costs associated with launching a tender, costs of equipment and materials; if devices are stored at decentralized levels, this may require travel, accommodation and per diem costs | Procurement agency or partner(s) | NMPs should be conscious of possible extended lead times for procurement of equipment and materials that will be imported given supply chain disruptions. Procurement procedures should be started early to avoid delivery delays.
Develop a supply chain management plan, including tracking tools, for all equipment and materials that will be used as part of the digitalization of the campaign |  | 8 to 10 months before distribution | No | The supply chain management plan should be developed by the digitalization and logistics sub-committees as part of their roles and responsibilities | NMP and digitalization sub-committee | It is important that there is a clear management strategy for moving the equipment and materials from the central to implementation levels, including inventory frequency and use of tracking tools. Decisions will need to be taken about who is responsible for transport and storage at different levels to ensure sufficient training is done for effective tracking of equipment and materials for digitalization.
Assess storage and security requirements for digitalization equipment and materials at all levels based on the supply chain management plan; where needed, contract appropriate storage locations if these are not freely available and ensure that insurance is contracted (either integrated in rental of storage locations or separately where storage locations are available free of charge) |  | 6 to 8 months before distribution | Yes | Costs associated with assessment (travel, per diem, etc.) and rental of storage space, security and insurance | Digitalization and logistics sub-committees | Digitalization equipment and materials include high value and relatively fragile items that may be at high risk for damage and theft. Safe storage is critical, especially at the implementation level. Consider needs for insurance for equipment and materials during transport, storage and implementation of activities.
Plan and budget for transport of materials and equipment to all planned storage points/locations (e.g. district health teams, health facility levels etc.) based on the supply chain management plan; it is important that devices are not combined with transport of other items to keep them in excellent condition |  | 6 to 8 months before distribution | No | The supply chain management plan should be developed by the digitalization and logistics sub-committees as part of their roles and responsibilities | NMP and digitalization sub-committee | The transport plans for equipment and materials at sub-national levels should be developed during the microplanning workshops at the same time as the micro transport plans for ITNs are developed.
Digitalization microplanning/digitalization landscape
Work with other sub-committees to include digitalization elements in the list of information to collect in advance of the microplanning workshops (e.g. mobile phone network coverage, including for internet; smartphone penetration; percentage of the population uses social media; social media platforms that are utilized in the targeted area, including their percentage of the market; electricity access; etc.) |  | 6 to 8 months before distribution | No | The list of information to collect in advance of microplanning should be developed by the digitalization sub-committee as part of its roles and responsibilities | Digitalization sub-committee | Review of each of the targeted districts for the ITN mass campaign, taking into account the context analysis (10a. to 10d. 11 and 12). | https://datareportal.com/, https://networkreadinessindex.org/, data from local institutions and companies
Ensure that the members of the national teams supporting the microplanning workshops include people focused on digitalization so that they can verify additional implementation level information with workshop participants (e.g. verification of availability of tools and equipment and their functionality; internet availability at health facility level; verification of network coverage data provided by network providers; etc.) |  | 6 months before distribution | No | Travel, accommodation, per diem; facilitation costs | ICT4D team | While it is recommended that microplans are developed 4 to 6 months before distribution, sometimes the activities are delayed leaving insufficient time for procurement of materials. If there are risks that microplanning workshops will be delayed or that procurement procedures will take a long time, it is recommended that the detailed implementation level planning for the digitalization takes place as a stand alone activity according to the digitalization timelines. | See Microplanning guidelines https://allianceformalariaprevention.com/tools-guidance/amp-toolkit/microplanning/
Develop a digitalization microplanning template to be used to ensure detailed operational level planning and budgeting for the implementation context |  |  | No | The digitalization microplanning template development should be led by the digitalization sub-committee and ICT4D team as part of their roles and responsibilities | Digitalization sub-committee/ICT4D team
Work with other sub-committees to review agendas and materials for the microplanning training of facilitators and workshops and ensure digitalization is included at all levels (e.g. digitalization focal points are invited as facilitators/participants) |  |  | No | The review of the agendas and materials for the microplanning is part of the digitalization sub-committee and ICT4D team TORs | Digitalization sub-committee/ICT4D team | If the number of days for the microplanning workshops is limited, consider splitting the digitalization team into a separate group to ensure sufficient focus on this aspect of the campaign.
Ensure that sufficient time is allocated during the microplanning workshops for the national regional, district and health facility digitalization focal points to work together on the specific approaches and risk mitigation planning for sub-national areas targeted for the campaign |  | 4 to 6 months before distribution | Yes | Travel, accommodation, per diem; facilitation costs | Digitalization sub-committee/ICT4D team
Ensure participation of members of the digitalization sub-committee and ICT4D team in review and verification of microplans and consolidation and validation workshops |  |  | Yes | Travel, accommodation, per diem; facilitation costs | Digitalization sub-committee/ICT4D team
Preparing for training and implementation
Working with other technical sub-committees, develop training agendas for the digitalization component for all actors involved with digital data collection at all levels; based on agendas, develop curricula to be used for training (either paper or device-based), including integration of digitalization elements into the campaign training manual or development of a separate training manual specific to digitalization |  | 6 to 9 months before distribution | No | The development or updating of the agendas and materials for the training is part of the digitalization sub-committee and ICT4D team TORs | Digitalization sub-committee/ICT4D team | It is important that sufficient time is allocated in training agendas for both the digitalization and other thematic areas. Based on the agendas developed with all technical areas included, it may be necessary to extend the number of days planned for training.
Develop user-friendly guides (either paper or device-based) describing the steps and procedures to be followed for each actor that will be involved in the digitalization aspect of the campaign; ensure that these include troubleshooting options and "who to contact" information in case of major challenges during implementation |  |  | No | The development or updating of the agendas and materials for implementation is part of the digitalization sub-committee and ICT4D team TORs | Digitalization sub-committee/ICT4D team | The guides developed for campaign actors with different roles and at different levels should be tailored and, as much as possible, should integrate information beyond the digitalization component. For example, if using digitalization for household registration, ensure that the guide for registration teams includes both digitalized (data collection) and non-digitalized processes (approaching households, introducing the team and the campaign to the household, social and behaviour change messages, marking of households, etc.)
Work with the technical and M&E sub-committees to adjust supervision and monitoring tools, checklists and SOPs that will be used by supervisors and monitors at each level to include aspects related to the digitalization; ensure that SOPs and protocols are updated in line with changes to the tools and procedures |  |  | No | The development or updating of the agendas and materials for implementation is part of the digitalization sub-committee and ICT4D team TORs | Digitalization sub-committee/ICT4D team | Note that the tasks for "general" supervisors will differ from those for digitalization-specific supervisors and ICT4D support. The tools and checklists for "general" supervisors and monitors should be focused on overall implementation of activities with a digitalization component rather than troubleshooting technical problems with devices, etc.
Develop a detailed plan and tools for the ICT4D technical teams that will be managing the digitalization component of the campaign, including device management and troubleshooting |  |  | No | The development or updating of the agendas and materials for implementation is part of the ICT4D team TORs | ICT4D team | Technical issues and challenges with devices, data collection and transmission, connectivity, etc. are likely to occur during the implementation of activities. In order to ensure that these are identified and managed quickly, the ICT4D team needs to develop a detailed plan that will allow for rapid response to technical issues for all areas targeted for digitalization. This includes standard channels for reporting issues and their resolution. Based on the plan developed, any additional requirements for technical staff should be flagged to the national malaria programme. The ICT4D teams should consider establishing and staffing an IT support helpdesk that can be contacted for troubleshooting.
Work with the M&E sub-committee to adjust the agenda and training materials for data managers to include the digitalization component, including the steps for daily cleaning, analysis and feedback based on data submitted |  |  | No | The development or updating of the agendas and materials for data managers is part of the digitalization sub-committee and ICT4D team TORs | Digitalization sub-committee/ICT4D team | Based on decisions taken related to the digitalization and the levels at which daily data review will take place, the training agendas, manuals and SOPs for data managers will need to be updated.
Training
Based on the training plan developed for the campaign, including for the digitalization, implement the trainings at all levels and for all campaign actors, including the digitalization component and data management |  | Based on training plan | Yes | Travel, accommodation, per diem, facilitation costs, tools and materials, etc. | Based on training plan, including ICT4D at all levels | Ensure that the central level training of trainers for implementation (household registration and distribution) includes sufficient time and practice with devices for participants that will be responsible for training at the next levels of the cascade. The quality of the central ToT will directly affect the quality of the subsequent trainings, so it is critical that ICT4D facilitators lead the training for digitalization sessions. The digitalization sub-committee and the ICT4D team should either facilitate or monitor training sessions at all levels to ensure that the digitalization component is well understood (which will reduce troubleshooting during implementation). The digitalization sub-committee and the ICT4D team must ensure that sufficient devices are on hand to allow training participants to practise with the tools, especially for primary data collection.
Implement pilot and full campaign
Implement the pilot in the identified geographic area and ensure that lessons learned are captured and system adjustments are made (where required) prior to full deployment of the system for the ITN campaign |  | As per digitalization timeline | Yes | All costs for operationalizing the pilot (training, campaign personnel, data managers, logistics, SBC, etc.) | NMP/ICT4D team | The pilot implementation must take place sufficiently early to ensure that any lessons learned or adjustments can be made before the full system is deployed.
Ensure that IT support is available in the implementation areas during both the pilot and the full deployment and that the helpdesk is functioning correctly |  | During implementation of pilot and broader campaign | Yes | Technical IT staff for helpdesk, communication cost, travel, accommodation, per diem costs | NMP/ICT4D team | Ensure that the helpdesk and IT support team are available and have all the necessary tools to provide technical support to campaign staff whenever teams are out in the field. ICT4D team members must be able to go out in the field to supervise, monitor and troubleshoot problems arising. ICT4D teams need to be responsible for device management during implementation, as well as regular back-up of primary data.
Supervise and monitor teams undertaking primary data collection; use checklists to identify any weaknesses and ensure that corrective action is taken early in the implementation of activities |  |  | Yes | Costs for supervision and monitoring (transport, accommodation, per diem, communication, etc.) | General supervisors and monitors, ICT4D teams | Problems are to be expected in the first days of the deployment of the system given the huge number of people using devices to collect the data. Supervision and monitoring plans must be developed to ensure maximum coverage of campaign actors in the first days of the activities to identify problem and implement corrective measures.
Ensure that data are transmitted as planned, compiled into the database and analysed each day; ensure daily feedback based on data received for timely corrective action |  |  | Yes | Costs for data managers, ICT4D team, supervision and monitoring (transport, accommodation, per diem, communication, etc.) | Data managers, ICT4D teams, M&E and digitalization sub-committees | The main advantage of digitalization is access to almost real-time data for decision-making. It is critical that data managers monitor the transmission of data and that teams are quickly identified that have not uploaded their data. The rapid compilation and analysis of daily data to provide feedback to supervisors and monitors is crucial for ensuring that implementation and data quality are high.
Post-distribution
Ensure that all devices, equipment and tools sent out to various levels for campaign implementation are collected, inventoried and prepared for transport based on the plan established for management of the devices at the end of the campaign |  | Within one week of the end of the campaign | Yes | Transport of devices to agreed level for storage | Digitalization sub-committee/ICT4D team | It is important that devices, equipment and tools are managed at the end of the campaign to avoid any loss or theft. As per the supply chain management plan, the devices should be inventoried and then tracked using the appropriate tools to ensure high accountability.
Ensure that all primary data collected have been securely stored/archived after the final data analysis and reports are available |  | Within one month of the end of the campaign | No | Part of the TOR for the ICT4D team and the data managers | NMP/ICT4D team | Primary data collected from the ITN campaign will have to be stored (or disposed of) as per the national laws and regulations. It is important that plans for the storage of data post campaign are described in the campaign plan of action.
Use post-distribution wrap-up meetings at all levels to gather information on successes and challenges and generate lessons learned and recommendations for future campaigns |  | Within three months of the end of the campaign | Yes | Rental of venues at all levels; transport and per diem for facilitators and participants; facilitation costs; refreshment and lunch breaks; stationery; etc. | NMP/ICT4D team | The wrap-up meetings should be used to identify successes, challenges, lessons learned and recommendations for future health campaign digitalization. The findings should be documented in detail and made available for teams planning for digitalization of other activities.
Note on I5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I think this should only be resources as “further information” can just be under “notes”.
Note on B21: ====== ID#AAAAS1kzbHU tc={86290DA2-E07F-4EA0-AD6E-34CDED622E62} (2021-12-09 16:10:58) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I wonder if the details of this (i.e. row 25-36) should be in a separate sheet, 'Outline of PoA'? Reply: Have added it as a separate worksheet