## ITN Campaign Assessments
Name and contact information
National Malaria Programme (NMP) Director
NMP ITN Campaign Focal Point
NMP M&E Focal Point
Partners In-Country
Date of update
ITN campaign assessment - Planning and implementation checklist
Steps | Description | Responsible | Timing | Good | In progress | Inadequate | Issues and mitigation | Notes
Preparation Operational guidance | Review ITN campaign operational guidance and plans pertaining to household registration (HHR), ITN distribution, or both
Step one: Review ITN campaign coordination structure and identify common understanding of campaign and assessment needs | Establish the ITN campaign M&E sub-committee
Develop a common understanding of campaign and assessment needs
Step two: Identify assessment goals, approach, objectives and primary ITN campaign indicators for a potential assessment | Identify assessment goals and approach
Identify assessment objective
Select priority assessment indicators, targets, and plan corrective actions
Step three: Decide whether to undertake an assessment | Review ITN campaign assessment needs and resources
Summarize key reasons and resource needs with the National Coordinating Committee (NCC) and national malaria programme leadership to make and validate decisions
Make a decision and inform stakeholders
Consider forming an assessment technical working group (TWG)
Step four: Design the assessment and develop assessment protocol | Select assessment tools and methods
Design the assessment
Select geographic area(s) based on risk and/or resources
Define assessment approaches for household data collection
Conduct real-time analysis of data
Analyze and classify lots (primarily for end-process assessments)
Following classification of lots - conduct investigation, identify potential actions and lessons learned
Develop, review, and finalize the assessment protocol
Step five: Develop assessment financial plan | Develop a budget
Identify and secure funding resources to cover assessment costs
Step six: Identify and plan recruitment of assessment teams | Select assessment teams
Identify number of surveyors and number of days needed to conduct assessments
Establish recruitment processes
Step seven: Develop assessment questionnaires | Draft the questionnaires
Prioritize questions to inform the assessment objective and indicators
Share the draft questionnaires with key ITN campaign partners for inputs
Translate final validated questionnaires
Pre-test and finalize the questionnaires
Step eight: Train assessment personnel | Develop the field survey manual
Organize training sessions
Step nine: Prepare and conduct data collection fieldwork | Coordinate with health and administrative authorities
Prepare data collection tools
Plan for data processing
Organize data collection fieldwork administration and logistics
Collect data
Ensure data quality control and assessment supervision
Step ten: Compile, analyse, report and use data | Recruit quality data processing and analysis support
Enter data electronically
Transmit data to a web database
Reinforce data security
Analyse the data
Include maps to visualize the results
Develop and disseminate reports