## Planning & budgeting checklist
Planning and budgeting checklist for ITN school-based distribution (SBD)
The activities contained in this checklist should be included in the ITN distribution timeline to ensure timely planning and implementation. This checklist should also serve as a basis for activities to be considered and then costed in the ITN SBD budget. The "Funding for what?" column should include as many details as possible for clarity during budget development and finalization. Who will fund and implement the activities may vary, and part of the macroplanning will include assigning roles and responsibilities to the national malaria programme and partners. The checklist may also identify gaps where resource mobilization is needed.
Steps for planning | Responsible | When? (timeline) | Funding required? | Funding for what? | Responsible | Notes | Further information and resources | Tick when completed
Coordination and channel selection
Within national malaria coordination structures, organize coordination and planning meetings and share information as needed between NMP and reproductive health (RH), Expanded Programme on Immunization (EPI), routine, community health service, national health information and health digitalization divisions, civil society, Ministry of Education (MoE), humanitarian and other sectors. |  | Minimum of 12 months before distribution | Yes/No | As needed - Transport and per diem (where applicable); rental of venue; facilitation costs; stationery - Technical experts (internal or external) | National malaria programme (NMP) National school health (or similar) department | MoH and MoE meeting venues and materials may be sufficient for meetings.
Review ITN access data in general and consider whether adjustments to the current ITN distribution channel selection and mix are needed. |  |  | Yes/No |  | NMP (Lead) World Health Organization (WHO) Other technical and implementing partners
For each channel currently being used, review how well the current mix of channels overall and each channel individually is functioning to achieve equitable, continuous and cost-effective ITN access. Assess each channel in terms of implementation costs (human resources, time and funding). |  |  | Yes/No |  |  |  | Add link to Guidance for Channel selection for further information.
Where local data are needed for decision-making, the NMP may also work with sub-national coordination structures already in place, such as provincial, regional and district health and education departments, to guide strategic direction, implementation and monitoring of interventions. |  |  | Yes/No |  |  | Any consideration of modifying current ITN distribution channels to include a different mix of channels will need to build on or maintain current strengths and address current weaknesses in the distribution channels in use.
Where new channels, including SBD, will be added to the ITN distribution channel selection mix, leverage available tools and resources and update ITN distribution TORs, national guidelines and training materials to include the operational aspects of planning and implementation. |  |  | Yes/No | As needed: - Technical experts (internal or external) - Guideline writer to support NMP | NMP |  | Add link to ITN SBD Toolkit and Adaptable tools (POA, Risk assessment and mitigation)
Macro-quantification - Considerations for ITN SBD
Convene the national malaria coordination structure, as appropriate, to prepare a macro-quantification plan to include in the ITN SBD Plan of Action (PoA). |  | 10 to 12 months before distribution | No |  | NMP | MOH and MOE meeting venues and materials may be sufficient for meetings. | Add link to the Downloadable Template
Use the ITN Quantification Site [Further information and resources column] to determine the appropriate population quantifier to estimate the quantity of ITNs required for distribution to achieve or maintain the target ITN access level. |  |  | No | If remote technical assistance is needed, contact NMP | NMP | The choice of population quantifier will depend on the programme’s overall ITN distribution strategy and the estimated ITN lifespan. The population quantifier can be applied to populations nationally or sub-nationally (e.g. district or region). How it is used depends on the country’s policy and strategy for continuous distribution. Quantifiers are presented for non-routine continuous distribution channels only, i.e. school-based distribution and community-based distribution. The ITN Quantification Site assumes that ITNs are also distributed to pregnant women at ANC and to infants at EPI visits using a population multiplied by 6%. | Link to the ITN Quantification Site. https://allianceformalariaprevention.com/itn-quantification/index.html#:~:text=What%20is%20the%20ITN%20Quantification,and%20estimates%20of%20ITN%20longevity.
Macro-quantification and estimating ITN SBD needs: collaborate with the Ministry of Education to obtain accurate attendance data for all primary schools and primary school classes in target geographical areas (including public, private and religious schools). Sum these data to calculate an aggregate figure. Transform the absolute enrolment figures into population percentages which can be compared to the population quantifier from the ITN Quantification Site. Use this information to estimate the number of classes required to be included to meet the population quantifier. |  |  | No | If remote technical assistance is needed, contact NMP | NMP and MoH | Note that enrolment data will likely be for the previous or current year while distribution will likely be planned for a future year, thus, consider applying aggregate drop-out and increment rates to estimate future aggregate enrolment. Official total population figures should be sourced from the National Institute of Statistics. | Add link to ITN SBD Toolkit Step Three.
Waste management - Considerations for ITN SBD
To be developed
Planning - Considerations for ITN SBD
Develop an ITN SBD Plan of Action (PoA) |  | 10 to 12 months before distribution | Yes/No | The development of the ITN SBD PoA is part of the NMP TORs, with MoE support, but funds may be required for a workshop for meetings (cost of venue rental, transportation, refreshment and lunch breaks, etc.) | NMP (Lead), MoE | The ITN SBD PoA should align with the National Malaria Strategic Plan and ITN distribution guidelines in place. | Add link to ITN SBD Adaptable POA tool and the ITN SBD toolkit.
Develop an ITN SBD Timeline |  |  | Yes/No |  | NMP (Lead), MoE |  | Add link to ITN SBD Timeline
Develop an ITN SBD Budget |  |  | Yes/No |  | NMP (Lead), MoE
Develop ITN SBD micro-quantification - Micro-quantification should use enrolment data from individual schools for the current school year, focusing on the targeted classes. - Data should include the number of students enrolled in the current year together with any anticipated drop-outs and planned new arrivals if known. - Compile data at district level and regional level to form the micro-quantifications. - Account for schools that may have been omitted or new schools that have opened since the macro-quantification data were collected. Be prepared to adjust ITN quantities based on changes in enrolment, such as mid-year admissions or drop-outs. - Address logistical challenges, such as transport to remote schools and storage of ITNs at school facilities. |  |  | Yes | Compiling, reviewing and validating enrolment data for the classes selected for SBD is part of the MOE TORs, but funds may be needed for communication, and some limited in-person follow-up or transport of records | MOE | Use the downloadable template to determine the number of ITNs required for each participating sub-national level (e.g. by province, region, district,school). Plan data collection for micro-quantification at the start of a school term in which the distribution will occur (see Step Five). This will help minimize the effect of changes in enrolment on quantification and planning. Depending on country context and level of coordination, consider conducting workshops with education and health officials at regional and district levels to discuss and finalize micro-quantification plans. | Add a link to the micro-quantification plan Downloadable Template
Develop an ITN SBD budget as part of the ITN SBD PoA - For detailed activities identified as part of ITN SBD Timeline develop a costing for a draft ITN SBD budget. - Identify and collect unit costs with the national malaria programme and partners from recent budget exercises for other health and malaria activities to inform the costing exercise. - Share the draft budget for review by the national malaria programme manager, financial and budget focal points at the NMP and partner organizations, and the national malaria coordination structure. |  |  | Yes/No | The development of the ITN SBD budget is part of the NMP TORs, with MoE support, but funds may be required for a workshop for meetings (cost of venue rental, transportation, refreshment and lunch breaks, etc.) | NMP | Use this ITN SBD Planning and Budgeting Checklist tool and review budget considerations. | Add link to the ITN SBD toolkit.
Logistics - Considerations for ITN SBD
Develop an ITN SBD logistics and supply chain plan as part of the ITN SBD PoA - Identify transport routes, storage and distribution points as well as plans for logistics to return surplus ITNs after issuing. |  | 8 to 10 months before distribution | Yes | The development of ITN SBD logistics plans and tools as part of the ITN SBD PoA are part of the NMP TORs Phone credit or travel costs may be needed to collect data from peripheral sites and/or to confirm logistics and supply chain details. Contracting third-partly logistics suppliers and/or other transporters and ITN handlers will also be needed. | NMP
Develop a logistics timeline, budget, tools, defined roles and responsibilities, reporting and oversight - as validated by the national malaria coordination structure. |  |  | Yes/No | The development of ITN SBD logistics plans and tools as part of the ITN SBD PoA are part of the NMP TORs Phone credit or travel costs may be needed to collect data from peripheral sites and/or to confirm logistics and supply chain details. | NMP
Develop a supply chain risk assessment to identify and mitigate opportunities for fraud, theft or diversion of ITNs. |  |  | Yes | ITN insurance needs to be considered | NMP
Develop an ITN SBD storage plan as part of the ITN SBD PoA - Instructions for calculating and verifying warehouse and storage space should be provided to each sub-national area and school. - Warehouse and storage quality should also be assessed using a standardized checklist, with results reported from schools to national level for planning. - Include guidance on ITN delivery location - central or sub-national levels. |  | 6 to 8 months before distribution | Yes | Budget items to consider include: - Warehouse and storage space rental if additional space is needed. - Warehouse and storage space improvements if space is available but needs locks for doors, rodent extermination, leak proofing, or other items. | NMP | Storage space can be measured in cubic metres, accounting for adequate walkways and safe height of stacked ITN bales, to ensure that ITN inventory can be regularly and easily verified. | Add link to the ITN SBD toolkit.
Develop a security plan for stored ITNs as part of the ITN SBD PoA. |  |  | Yes | Budget items to consider include: adequate personnel to guard ITNs while in storage; assessment and upgrading of storage infrastructure as needed to provide closeable, lockable doors, windows, and other potential entry and exit points, drawing on information gathered through the warehouse and storage instructions and quality checklist. | NMP | Plan to store ITNs for a maximum of 1-2 days at schools prior to their distribution, to reduce theft risk.
Develop an ITN SBD transport plan as part of the ITN SBD PoA. |  |  | Yes | Budget items to consider include: contracting transporters; personnel to load and unload ITN bales; costs for re-bundling ITNs where schools need fewer than a full bale of ITNs. | NMP | Given the reach of schools into communities, ITN transport is often challenging with some schools accessible only by boat, motorcycle, bicycle, or on foot.
Develop a plan for ITNs remaining after ITN SBD, as part of the ITN SBD PoA. For example, this may indicate the need to provide the leftover ITNs to teachers, other students, or to health facilities for distribution via routine ANC and EPI interventions. |  |  | Yes | Budget items to consider include: transport from schools to health districts or health facilities; tracking ITN movement and collecting data post ITN SBD. | NMP | Health facilities play an important role in receiving surplus ITNs following the ITN SBD activity, and managing these according to the SBD Plan of Action. This may include absorbing surplus ITNs into distribution via routine ANC/EPI services or logistics to redeploy surplus ITNs following ITN SBD issuing, as instructed.
Develop and disseminate ITN SBD logistics tracking and reporting tools (paper or digital equivalent). |  |  | Yes | Budget items to consider include: reproduction and transport costs for paper tools; tool development and testing for digital tools. | NMP | Tools include: - Requisition forms and/or supply forms for ITNs and supporting materials - Bin/stock cards to record the name and signature of warehouse personnel receiving and/or issuing ITNs and support materials, e.g. [Add hyperlinks] warehouse assessment and tools, waybills and SOPs, stock sheet and SOPs. - Transport waybills to record the movement of ITNs from one point (A) to another point (B) and ensure accountability from one level of the supply chain to the next.
Personnel - Considerations for ITN SBD
Personnel should be mobilized at all levels from among key ITN SBD stakeholders: MOH, MOE, sub-national administrative departments and authorities. |  | 6 months before distribution | Yes | Budget items to consider include: standard MoH transport and per diem (where applicable) for training, supervision, data collection, or other duties requiring more than one day away from personnel homes. | NMP | Payments to personnel involved in ITN SBD should leverage existing MoE and MoH systems, and collect the necessary information to complete the transactions in a timely manner.
Training - Considerations for ITN SBD
Develop an ITN SBD training plan as part of the ITN SBD PoA. |  | 6 to 9 months before distribution | Yes/No | The development of the ITN SBD PoA is part of the NMP TORs, with MoE support, but funds may be required for a workshop for meetings (cost of venue rental, transportation, refreshment and lunch breaks, etc.). | NMP | As SBD is conducted annually, training or refresher orientation may be needed annually as well.
Develop ITN SBD training materials, including: - Pre- and post-assessments - Training agenda and user-friendly curricula and training guides - ITN SBD reporting tools, key messages and other job aids which participants will be trained to use - Checklists to organize trainings, including samples of materials, stationery and management tools (e.g. the MoH directives on training, instructions to trainers) |  |  | Yes | Materials development may require a workshop or similar meeting, funds may be required for a workshop for meetings (cost of venue rental, transportation, refreshment and lunch breaks, etc.). Where ITN SBD is conducted annually, material development may not require significant updates, allowing a focus on materials production and dissemination. | NMP
Conduct standalone or integrated Training of Trainers cascade training or direct training. |  | Based on training plan in the ITN SBD PoA | Yes | Budget items to consider include: travel, accommodation, per diem, facilitation costs, tools and materials, and other training costs. | NMP | The ratio of trainers to trainees and number of hours/days needed for training will vary at different levels of the health and education systems. More time will also be needed the first time that ITN SBD is conducted.
Social and behaviour change (SBC) - Considerations for ITN SBD
Develop an evidence-based ITN SBD SBC plan, as part of the ITN SBD POA. |  | 6 to 9 months before distribution | Yes/No | The development of the ITN SBD PoA is part of the NMP TORs, with MoE support, but funds may be required for a workshop for meetings (cost of venue rental, transportation, refreshment and lunch breaks, etc.). | NMP | ITN distribution SBC plans should include channel-specific approaches. For ITN SBD SBC planning, objectives and approaches should align with the national malaria SBC Plan and the RBM SBC Strategic Framework and Resources and include: - Integration of SBC plans for ITN distribution within existing malaria SBC materials - ITN communication strategies and activities - Development and production of SBC materials for ITN distribution
Develop ITN SBD SBC materials, which may include: - Key messages for advocacy with health, education, and administrative authorities; private sector partners; technical; and other stakeholders - Key messages and interpersonal communication approaches for social mobilization and for engaging youth in health and malaria to bring powerful youth voices to health SBC - Planning for rumour management - Ads, testimonials, and key information shared through: ---Mass media: radio and/or television ---Social media ---Print media ---Interpersonal communication |  | Based on SBC plan in the ITN SBD PoA | Yes | Materials and guide development may require a workshop or similar meeting, so funds may be required (cost of venue rental, transportation, refreshment and lunch breaks, etc.). Where ITN SBD is conducted annually, material development may not require significant updates, allowing a focus on materials production and dissemination. | NMP (Lead), MoE
Adapt and develop teachers' malaria guides, including: - A health activity planning template - Steps for malaria-free schools and communities - Fundamental information on malaria - Key messages for key audiences - Activities for school assemblies - Classroom and community activities - Sample discussion questions |  | Based on SBC plan in the ITN SBD PoA | Yes |  | NMP (Lead), MoE
Issuing ITNs - Considerations for ITN SBD
ITN issuing guidance should be developed for eligible classes, as part of the ITN SBD PoA. Guidance should be shared with all involved in ITN distribution day, and included as a key component of ITN SBD training and tools. |  | 6 to 9 months before distribution | Yes/No | The development of the ITN SBD PoA is part of the NMP TORs, with MoE support, but funds may be required for a workshop for meetings (cost of venue rental, transportation, refreshment and lunch breaks, etc.). | NMP | Issuing guidance may be shared electronically. Alternatively, it may be determined that paper-based guidance is essential, and costs for producing the written guidance and ensuring its transport and disssemination alongside other paper-based tools will be necessary.
In case the number of eligible students present on ITN distribution day exceeds the number of planned ITNs, consider organizing small ITN buffer stocks to be available at schools or at sub-national medical stores. |  | Within one week before the ITN SBD | Yes | This can be part of the ITN SBD transport plan, as noted above. | NMP | Use of off-site buffer stocks in existing SBD programmes has been low, in part because of the high accuracy of SBD planning as well as the logistical challenges of accessing off-site stocks.
The head teacher/classroom teacher/health educator are often responsible for ITN issuing. As part of accountability planning, identify more than one teacher and/or school administrator to be involved in issuing, recording, aggregating, validating and reporting data. |  | ITN SBD distribution day | No | In general, monetary incentives beyond training per diems are not recommended for ITN SBD. | Teachers
ITNs should be issued to students on the designated distribution day, accompanied by communication as per the SBC planning in the ITN SBD PoA. |  | ITN SBD distribution day | No |  | Teachers | See ITN SBD SBC materials and teachers' malaria guide above.
Supervision - Considerations for ITN SBD
Supervision guidance should be developed and included in the ITN SBD PoA to reinforce ITN SBD accessibility and quality objectives. |  | 6 to 9 months before distribution | Yes/No | The development of the ITN SBD PoA is part of the NMP TORs, with MoE support, but funds may be required for a workshop for meetings (cost of venue rental, transportation, refreshment and lunch breaks, etc.). | NMP | The plan should include an approach to sampling and selecting sub-national areas (e.g. provinces, districts,) schools, communities, and/or health facilities to visit; clear roles and responsibilities for each supervisor cadre; supervision checklists to collect information and insights on ITN SBD quality and effectiveness; a timeline; as well as approaches for communicating and addressing challenges as they arise.
Supervision tools should be developed for ITN SBD personnel across levels: - Supervision checklists developed with and validated by the national malaria programme and ITN SBD Department of Education. Checklist forms may include a review of adherence to procedures, SBC, quality of service and ITN provision. - Supervision reports should be collated and findings used to inform planning for subsequent rounds of ITN SBD and to describe roles and responsibilities. |  |  | Yes/no | Tools development may require a workshop or similar meeting, so funds may be required (cost of venue rental, transport, refreshment and lunch breaks, etc.). Where ITN SBD is conducted annually, material development may not require significant updates, allowing a focus on materials production and dissemination. | NMP
Conduct supervision: successful implementation of ITN SBD requires supervision at many levels. At least once during ITN SBD, focal points and/or coordination teams at: - National health and education levels should conduct supervision visits to a selection of sub-national, sub-sub-national and/or school levels. - Sub-national, (e.g. regional) health and education levels should conduct supervision visits to a selection of sub-sub-national (e.g. districts) and schools implementing ITN SBD. - Sub-sub-national (e.g. district) health and education levels should conduct supervision visits to a selection of sub-district and schools implementing ITN SBD. |  | According to the ITN SBD supervision plan | Yes | Budget items to consider include: travel, accommodation, per diem, facilitation costs, tools and materials, and other supervision costs. | NMP | Primary objectives include: to observe ITN SBD, logistics, data collection; identify challenges and support sub-national colleagues in troubleshooting and overcoming challenges, and promote ongoing improvement of ITN SBD implementation and results.
Monitor and evaluate the ITN SBD
M&E planning should be carefully designed at the outset as part of the ITN SBD PoA and ITN SBD M&E planning approach. |  | 6 to 9 months before distribution | Yes/No | The development of the ITN SBD PoA is part of the NMP TORs, with MoE support, but funds may be required for a workshop for meetings (cost of venue rental, transportation, refreshment and lunch breaks, etc.). | NMP (Lead), MoE | Consider suitable M&E systems: - Determine whether data collection and reporting will occur using an existing data collection and reporting system or one created specifically for school-based ITN distribution. - Determine whether data collection and reporting will be paper-based or digital. Digital approaches are preferred and strongly recommended. Data collection and reporting tools should be developed accordingly. - Budget accordingly: a data collection and reporting system specific to school-based ITN distribution may require additional training or procurement if appropriate systems are not already in place. - Similarly, resources for digital data collection and reporting system may require additional training or procurement of electronic devices.
Additional evaluation through household surveys should be planned to understand how ITNs delivered through SBD contribute to maintaining levels of ITN access in households. |  | 6 to 9 months before distribution | Yes/No | As needed, household surveys will need to be budgeted.
Ideally, monitoring should flow through existing systems. However, there may not be an existing health reporting structure within which SBD can work; therefore, it will need parallel reporting systems. Activities that may be useful to routinely monitor include: - Quality of trainings - Supply chain processes - Assessment of SBC activities against plans - Distribution, through the collation and analysis of ITN distribution data - Supply chain processes |  | 6 to 9 months before distribution | Yes/No | Budget items to consider include: standard MOH transport and per diem (where applicable) for data collection, or other duties requiring more than one day away from personnel homes. |  | Guidance can be drawn from campaign style monitoring . | Add link to the Alliance for Malaria Prevention [AMP] toolkit for guidance.
Ensure that all primary data collected have been securely stored/archived after the final data analysis and reports are available. |  | Within one month of the end of ITN SBD | No | Part of the TOR for the ICT4D team and the data managers. | NMP/ICT4D team | Primary data collected from the ITN campaign will have to be stored (or disposed of) as per the national laws and regulations. It is important that plans for the storage of data post campaign are described in the campaign plan of action.
Use post-distribution wrap-up meetings at all levels to gather information on successes and challenges and generate lessons learned and recommendations for future campaigns. |  | Within three months of the end of the campaign | Yes | Budget items to consider include: rental of venues at all levels; transport and per diem for facilitators and participants; facilitation costs; refreshment and lunch breaks; stationery; etc. | NMP/ICT4D team | The wrap-up meetings should be used to identify successes, challenges, lessons learned and recommendations for future health campaigns. The findings should be documented in detail and made available for future planning.
Post-issuing
The approach to managing leftover ITNs may vary by country. For example, (1) teachers or other ITN SBD stakeholders may be tasked with managing the distribution of left-over ITNs to pupils in non-eligible classes; or (2) Sub-national medical storekeepers (warehouse managers) may be responsible for receipt, tracking and issuing of surplus ITNs to sub-national health teams for distribution through routine health services, e.g. ANC and EPI; or (3) other approaches may be adopted for use of ITNs remaining after the ITN SBD activities. |  | Within one month of the end of ITN SBD | Yes/No | If needed, logistics costs for sending remaining ITNs to sub-national (e.g.district) medical storekeepers or other reverse logistics endpoints, as determined in the ITN SBD POA. | NMP (Lead) in collaboration with the MoE
Plan to maintain SBC through school-health programme messaging to reinforce malaria prevention and use of the ITNs. Furthermore, while ITNs are distributed to schoolchildren, it is important to reinforce that the ITN is for the household. Pilot programmes have shown that students may feel that the ITN belongs to them. SBC should include messages and approaches to reinforce that the ITN is for the whole household. |  | In the months following ITN SBD, prior to the subsequent ITN SBD | Yes/No | Planning should include provision for the development of SBC materials to be used both during ITN SBD as well as throughout the school year. A small budget may be needed for additional materials production for the post-issuing period. | NMP