## Risk a'ment and mitigation plan
SCHOOL-BASED DISTRIBUTION OF ITNs
EXAMPLE RISK ASSESSMENT AND MITIGATION PLAN
Adaptable tool
Area | Risk | Risk category | Likelihood | Impact | Heat map | Early warning signs | Key controls / mitigation plan | Tools required | Risk owner | Timeline, relative to planned distribution
ITN quantification / procurement | Inaccurate needs estimation, due to outdated or inaccurate census or enrolment data. | Operational | Possible (2) | Significant (4) |  | Unavailable or inaccurate enrolment data for quantification | - Conduct thorough macro- and microplanning with the latest school enrolment data and adjust forecasts as necessary at microplanning. - Include a buffer stock (e.g. +5-10%) to cover unexpected demand. - Plan a redistribution mechanism where surplus nets from low-uptake areas can be quickly transferred to higher-need areas. | Quantification tool, data collection tools | NMP | 8-9 months prior
| Long lead times for ITN procurement from international suppliers (9-12 months), delaying distribution. | Operational | Possible (2) | Significant (4) |  | Procurement timelines exceeding planned schedules | Engage suppliers early. | SBD POA | NMP | 8-12 months prior
Planning | Unplanned school closures (strikes, political issues, natural or man-made disaster) or scheduling conflicts (exams, holidays) disrupt the distribution timeline. | Operational | Likely (3) | Significant (4) |  | Political instability, major school calendar changes, or education funding shortfalls | Engage key stakeholders early and integrate contingency planning. | Risk assessment framework | MoH / NMP | Ongoing
| School closures due to health outbreaks (e.g. COVID, cholera), disrupting planned ITN distribution. | Operational | Likely (3) | Significant (4) |  | Reports of rising cases in schools or communities | Develop alternative distribution methods, such as community-based distribution. | Contingency plan | MoH / NMP | Before and during distribution period
| Poor coordination among stakeholders leading to overlaps or gaps in distribution. | Strategic | Likely (3) | Moderate (2) |  | Conflicting school distribution schedules, confusion over roles | Establish clear governance structure and hold regular coordination meetings. | Stakeholder matrix | SBD Working Group (WG) (or equivalent) chair | Monthly planning meetings, bi-weekly just before implementation
Logistics and supply chain | Limited ITN availability, restricting the number of participating districts and schools. | Operational | Possible (2) | Significant (4) |  | Unconfirmed commitments from funding partners prior to campaign | Follow up closely with donors and partners to confirm commitments. |  | MoH | Confirm before procurement begins
| Third-party logistics (3PL) transporters delivering ITNs to higher administrative level rather than to individual schools, causing logistical delays | Operational | Possible (2) | Significant (4) |  | Unconfirmed drop-off points at schools | `- Verify and confirm storage and delivery logistics before last-mile delivery. - 3PL contracts should clearly state the final point of delivery. | 3PL contracts and terms | MoH / SBD WG | One month prior to last mile delivery
| Failure to validate school enrolment and attendance data before distribution, causing reallocation and delays. | Operational | Possible (2) | Significant (4) |  | Unvalidated school enrolment data with the individual schools | Validate school enrolment data from MoE and schools before allocation of the ITNs to the schools. | Data validation tool | NMP/MoE
| Theft or misappropriation of ITNs before distribution, leading to losses and shortages | Financial / reputational | Likely (3) | Significant (4) |  | Reports of missing ITNs from storage or suspicious handling | Strengthen tracking and security measures for ITN storage and distribution. | Stock tracking system | MoH / NMP | Ongoing
Training | Distribution staff/teachers are not sufficiently trained, leading to errors (e.g. miscounted nets, uneven distribution) or slow processes | Operational | Likely (3) | Significant (4) |  | New or temporary staff may lack experience without proper training | - Conduct comprehensive training sessions and refresher courses for all distribution personnel. - Provide clear distribution guidelines, checklists, and on-site supervision especially in the initial days. | Training manuals and videos, quick-reference job aids, a communication channel (e.g. WhatsApp group) | NMP | Training to be completed two weeks before distribution
Social and behaviour change (SBC) | Limited funding for SBC activities, affecting awareness and behaviour change efforts | Financial | Possible (2) | Significant (4) |  | Unconfirmed funding commitments | Follow up closely with partners to secure SBC funding. | Budget tracker | NMP / SBC team members | Before campaign launch
| Low community participation and awareness, leading to ITN misuse or underutilization | Operational | Possible (2) | Moderate (3) |  | No or limited community engagement activities | Conduct extensive community mobilization and awareness campaigns. | Community engagement plan | NMP / SBC team members | Before and during distribution period
| Delays in community engagement efforts, reducing the impact of SBC messaging. | Operational | Possible (2) | Moderate (3) |  | Late initiation of SBC activities before distribution | Plan early community engagement and leverage school networks for awareness. | Community mobilization strategy | NMP / SBC team members | 3-6 months before distribution period
Implementation | High pupil absenteeism on the day of ITN distribution, affecting coverage. | Operational | Possible (2) | Significant (4) |  | High school absenteeism rates before distribution | Work with schools to schedule distributions on optimal attendance days. | School attendance records | NMP / MoE | During distribution
| Teachers requesting ITNs for personal use, reducing nets available for students. | Operational | Possible (2) | Moderate (3) |  | Reports of teacher requests for ITNs | Clearly communicate eligibility criteria to school authorities. | SBD distribution POA | NMP / MoE | Before distribution
Monitoring and evaluation | Unclear data management roles between MoH and MoE, leading to gaps in reporting and accountability. | Operational | Possible (2) | Significant (4) |  | Lack of clarity on reporting structures | Clearly define roles, responsibilities, and tools for data collection and reporting. | M&E framework | NMP / M&E team members | Before campaign monitoring starts
| Data discrepancies between school records and MoE figures, leading to under- or over-allocation. | Financial | Possible (2) | Moderate (3) |  | Differences in enrolment figures across data sources | Cross-check school records with MoE enrolment data at multiple stages. | Data validation tool | NMP / MoE | Before distribution
| Data system failure or downtime (loss of digital records) | Operational | Possible (2) | Moderate (3) |  | System slowdowns or crashes during implementation, lack of data backups | Regular data backups and IT support on standby during distributions | Backup servers/storage | IT manager and data manager (MoH/MoE) | Before and during distribution
Likelihood and impact scale
Likelihood |  | Impact
1 Unlikely |  | 1 Negligible
2 Possible |  | 2 Insignificant
3 Likely |  | 3 Moderate
4 Almost certain |  | 4 Significant
Heat map
Impact
Likelihood | 1 Negligible | 2 Insignificant | 3 Moderate | 4 Significant
1 Unlikely
2 Possible
3 Likely
4 Almost certain