|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **SN** | **Activity** | **Duration** | **Total Number of participants** | **Timeline** | **Venue** | **Facilitators** | **Comments** |
| 2 | Training of Zonal heads and EHTs | 1 day | 48 Chipangali, 43 Chadiza, 54 Katete, 61 Petauke | 23rd -24th September, 2021 | Katete, Chadiza, Chipangali, Petauke | MEO/SHN coordinators | Following the total number of partiocipants per district, trainings will be split in 2 hence venue will be hired for 2 days despite it being a 1 day training. This is to to observe the C19 guidelines. |
| 3 | Training of school teachers and SHIN coordinators | 1 day |  | 27th -30th September 2021 | Katete, Chadiza, Chipangali, Petauke | EHTs/Zonal heads | No venue required as trainings will be held at the various schools. |
| 4 | Distribution | 5 days |  | 4th -8th October 2021 | Katete, Chadiza, Chipangali, Petauke | Class Teachers | Distribution will be conducted by teachers in the varios classromms |
| 5 | Supervision | 5 days |  | 4th -8th October 2021 | Katete, Chadiza, Chipangali, Petauke | Central, Provincial and District Teams | Supervision will be conducted by all levels (Central, Provincial, District) |
|  | Submission of reports/data entry | 3 days |  | 9-11 October 2021 | Katete, Chadiza, Chipangali, Petauke | EHTs/Zonal heads |  |
| 6 | data entry | 5 days |  | 12th – 15th October 2021 | Katete, Chadiza, Chipangali, Petauke | MEOs |  |

**LLIN School Based Distribution Roadmap Eastern province**