## Timeline
This adaptable timeline has been developed from country examples. Activities are categorized under three headings: SBD planning, SBD implementation, and Review and modify SBD activities. The template includes rows for key upstream considerations for coordination, channel selection, macroquantification and waste management. The rows are included as a reminder that these activities should be completed prior to starting detailed implementation planning for school-based distribution. The SBD Distribution Toolkit can be reviewed for more details. Suggestions for the Key output from each activity and the usual Responsible party have been included for guidance. Users should modify the template, including editing activities, to meet their needs.
[YEAR] [COUNTRY] SBD Implementation schedule |  |  |  |  | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month 6 |  |  |  | Month 7 |  |  |  | Month 8 |  |  |  | Month 9 |  |  |  | Month 10 |  |  |  | Month 11 |  |  |  | Month 12
Activity | Resources | Key output | Responsible | Duration | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
These activities and documents should exist prior to detailed implementation planning for school-based distribution, but they do not necessarily need to be tracked in this timeline. They are included here for reference.
Upstream considerations (Coordination, channel selection, quantification, waste management)
Draft ITN strategy |  | Draft ITN distribution strategy
Field assessment of ITN channels |  | Field assessment report
Finalize ITN strategy |  | Final ITN distribution strategy
Source school enrolment data for target geographical areas |  | Recent school enrolment data
Quantify ITN need (macro-quantification) and identify target school grades | ITN Quantification Site | Macro-quantification plan, including SBD
Develop/revise SBD-specific waste management guidance |  | Waste management plan, including SBD
SBD Planning
Routine coordination, review and planning meetings |  | Action points following each meeting | NMP
Define and share TORs for key SBD roles | [Link to Adaptable Tool] | TORs | NMP
Develop/revise SBD Plan of Action | [Link to Adaptable Tool] | SBD Plan of Action | NMP
Develop/revise SBD Risk assessment and mitigation plan | [Link to Adaptable Tool] | SBD Risk assessment and mitigation plan | NMP
Develop/revise SBD Implementation guidelines |  | SBD Implementation guidelines | NMP
Source school enrolment data for target geographical areas |  | Recent school enrolment data | MoE
Develop annual microquantification plan at school-level |  | SBD Microquantification plan | NMP
Develop/revise SBD budget | [Link to Adaptable Tool] | SBD Budget | NMP
Develop/revise SBD timeline | [Link to Adaptable Tool] | SBD Timeline | NMP
Procure ITNs (timing to consider manufacturer and delivery lead times) |  |  | NMP
Develop Logistics and supply chain management plan / update existing plan with SBD considerations |  | Logistics and supply chain management plan | Logisticians
Develop Accountability plan / update existing plan with SBD considerations | [Link to Resource] | Accountability plan / Supply chain risk assessment | NMP
Identify storage locations and logistics personnel needs |  |  | Logisticians
Adapt tracking tools and other logistic tools (according to need) |  | Logistics tools | Logisticians
Contract third-party logistics company (according to need) |  | Third-party logistics contract(s) | NMP
Receive ITNs at port when delivered |  |  | Logisticians
Develop/revise SBD training plan, including training materials | [Link to Resources] | Training plan, materials and guides | NMP
Decide on training approach (direct training to all levels or cascade training) |  |  | NMP
Identify trainers |  | Master trainers identified | NMP
Source and confirm training venues |  | Training venues booked | NMP
Organize training materials and resources |  | All training preparations complete | NMP
Procure communication credit for SBD teams |  |  | NMP
Develop SBC plan / update existing plan with SBD considerations |  | SBC plan for SBD | NMP
Develop SBC materials for SBD |  |  | NMP
Print / mass-produce SBC materials |  | SBC materials for SBD | NMP
Ensure SBC considerations are included in SBD training activities |  |  | National trainers
Contract SBC provider, as needed |  | SBC contract(s) | NMP
Develop M&E plan / update existing plan with SBD considerations | [Link to Adaptable Tool] | M&E Plan | M&E staff
Develop routine monitoring tools |  |  | M&E staff
Print / mass-produce routine monitoring tools (when paper based) |  | SBD routine monitoring tools (paper) | M&E staff
Develop and test digital monitoring tools, including integration with existing systems |  | SBD routine monitoring tools (digital) | M&E staff
Develop evaluation tools (e.g. for household surveys), as needed |  | Evaluation protocol, including tools | M&E staff
Ensure M&E considerations are included in SBD training activities |  |  | National trainers
Share M&E plan and tools with cadres at appropriate operational levels |  |  | M&E staff
Contract external monitoring provider, as needed |  | M&E contract(s) | NMP
SBD implementation
Logistics: transport ITNs from national to sub-national levels |  | ITNs securely stored at sub-national levels | Logisticians
Validate class enrolment data prior to transporting ITNs to schools |  |  | School staff and logisticians
Logistics: transport ITNs from sub-national level to schools |  | ITNs securely stored at schools | Logisticians
Train national cadres (training of trainers) |  | Pre-post training assessments | National trainers
Train sub-national cadres (training of trainers) |  | Pre-post training assessments | National trainers
Train school cadres (teachers/health educators/headteachers) |  | Pre-post training assessments | Sub-national cadres trainers
Conduct pre-campaign SBC activities
Distribute ITNs to schoolchildren |  |  | School staff
Supervise ITN distribution activities |  | Supervision checklists submitted | Supervisors
Conduct distribution period SBC activities
Complete routine monitoring data (paper or digital) and submit data |  | Routine monitoring data submitted | School staff and M&E staff
Reverse logistics: document excess ITNs and implement transport plan |  | Excess ITNs secured at destination(s) | Logisticians
Conduct post-distribution period SBC activities
Conduct evaluation activities, if planned |  |  | M&E staff
Analyse routine monitoring data and any evaluation data |  | Distribution M&E reports | M&E staff
Review and modify SBD activities
Reconcile expenditures against budget and finalize SBD accounts |  | Reconciled financial accounts | NMP
Gather inputs from SBD stakeholders |  |  | NMP
Hold annual SBD process review meetings at sub-national level |  | Synthesis of success and challenges at sub-national levels | NMP
Hold annual SBD process review meeting at national level |  | Costed recommendations and actions for subsequent SBD | NMP
Implement action points from annual review |  |  | NMP