Digitalization plan of action (DPoA) for a mass ITN distribution campaign

V1. January 2026

The guidance in this document is intended for national malaria programmes (NMPs) starting macroplanning for their upcoming insecticide-treated net (ITN) mass campaign. It outlines the key items to include in a digitalization plan of action (DPoA) to support achievement of objectives defined in the overall ITN campaign plan of action. Digitalization is a tool for improving efficiency and outcomes of campaigns and it supports the technical/operational strategy defined for different campaign components. It is critical that the campaign strategy is determined based on experiences and lessons learned and that the DPoA, an annex to the campaign plan of action (PoA), describes how digital tools will be used in support of achieving the campaign objectives. Note that NMPs with limited experience in digitalization are strongly advised to develop a standalone DPoA, while NMPs with more experience may wish to incorporate sections from the DPoA in the overall campaign plan of action.

Contexts will vary, and NMPs should include information that is related to their specific situation and context. National malaria programmes should replace the suggested text with their own narrative.

Before developing the DPoA, NMPs are strongly encouraged to complete the AMP Campaign digitalization matrix. This tool will generate much of the information needed to fill in the sections of the plan and guide decision-making. It is particularly important for programmes that have not previously digitalized campaigns, or that are considering changes to the scope, scale, or digital platform used for previous campaign digitalization.

The Campaign digitalization matrix is made up of:

- Operational needs: The operational needs section of the decision-making matrix is designed to support NMPs to think about their operational needs in detail. This process allows countries to (1) understand and align on the need and reason to digitalize the campaign, and (2) determine the scope and scale at which digitalization may be possible or required.

- Context analysis: The context analysis section of the decision-making matrix is designed to support NMPs to analyse the context in which they operate, particularly the different elements that may affect digitalization. The context analysis helps NMPs consider how to plan and budget for the digitalization of the different components of their ITN mass campaign, leveraging on identified existing digitalization initiatives and experiences within the country.

- Planning and budgeting checklist: The planning and budgeting checklist brings together the operational needs and context analysis sections. It lists the steps that NMPs should consider to properly plan and budget for the digitalization of all or parts of their ITN mass campaigns. The planning and budgeting checklist should be used to develop the DPoA and the detailed budget regardless of previous digitalization experience. View the Checklist.

- Risks: This section lists examples of the potential risks associated with digitalization of campaign activities by campaign area, as well as possible mitigating measures that national malaria programmes should consider when developing the risk assessment and mitigation plan for the deployment of digitalization. This list is an example only and is not exhaustive of all possible risks associated with digitalizing an ITN campaign. NMPs should develop a risk register regardless of previous experience with digitalization. View the Risks and possible mitigation measures for digitalization of ITN mass distribution for further guidance.

See also the three generic plan of action templates for national malaria programmes to follow when preparing their macroplans:

Campaign plan of action

Logistics plan of action

Social and behaviour change plan of action

DIGITALIZATION PLAN OF ACTION (example of table of contents) Title page – logos, date of draft (country specific) Table of contents Acronyms and abbreviations List of tables List of figures - Introduction and purpose of digitalization plan of action (i) Summary of campaign (ii) Map of country showing target areas (iii) Purpose of the digitalization plan of action (iv) Accompanying documents - National digitalization landscape and context (i) National context for digitalization (ii) Digitalization lessons learned from previous campaign(s) or other experiences and recommendations for current campaign (iii) Objectives and scope of the campaign digitalization - Overall digitalization strategy (i) Platforms and apps selection (ii) IT infrastructure and policy (iii) Hardware management and storage (iv) Quantification of campaign personnel and mobile devices (v) Digitalization quantification and macro logistics (vi) Digitalization procurement and delivery (macro logistics) (vii) Other equipment, tools, services and materials procurement and delivery (macro logistics) - Planning and coordination of campaign digitalization (i) Digitalization coordination mechanism (ii) Responsibilities of the Digitalization Sub-committee (iii) Roles and responsibilities of digitalization partners - Implementation and technical support (i) Data collection and management during household registration/distribution (ii) Data management, reconciliation and feedback systems (iii) Incidents and technical support (iv) Supervision and monitoring (v) Accountability of devices, tools and materials (vi Security and incident management - Training and capacity-building (i) Recruitment and training of campaign personnel (ii) Digitalization training plan - Configuration, test and validation of digitalization platform and tools – pilot (i) Pretesting of the digital devices and software/user acceptance test (UAT) (ii) Pilot of the digitalization process and application - Digitalization risk assessment and mitigation - Post-distribution digitalization activities - Documentation, reporting and follow-up Annexes

Table of contents

- Acronyms and abbreviations: define acronyms and abbreviations the first time they appear in the narrative text.

- List of tables.

- List of figures.

All tables, figures, boxes, etc. to be numbered and referred to in the narrative text (to introduce them/explain the content).

1. Introduction and purpose of digitalization plan of action

(i) Summary of campaign

- Brief section (1—2 paragraphs copied and pasted from the introduction to the overall campaign PoA) introducing the campaign and giving a brief summary: planned dates, whether national or sub-national, rolling, etc. Describe the ITN distribution strategy or strategies (e.g. door-to-door or fixed site or other model or hybrid, such as door-to-door in urban areas and fixed site in rural areas) and the duration of the household registration and ITN distribution. Describe major differences in strategy (such as for urban and rural or complex operating environments) if applicable, as well as any ITN targeting decisions.

- Provide the overall campaign goal and the specific objectives for each phase of activity (from the overall campaign PoA). For example:

  - At least 95 per cent of households in all communities (rural and urban) are aware of the campaign strategy/ies with key details about distribution points and dates of the campaign.

  - At least 95 per cent of households are registered and issued vouchers to redeem their ITNs.

  - At least 95 per cent of registered households redeem their ITNs in both rural and urban areas.

  - At least 85 per cent of households that receive ITNs are hanging and using them

- Provide a table with a summary of the campaign, including scale, number of people targeted, number of ITNs planned for distribution and type of ITNs that will be distributed (see example and copy from the overall campaign PoA).

Table XX: Adapt to country context

| Target population |  |
| --- | --- |
| Scale of campaign (e.g. national in four phases or waves) |  |
| Total number of ITNs and funding partner (e.g. Global Fund, United States President’s Malaria Initiative, Against Malaria Foundation, government, etc.) |  |
| Number of ITNs to be distributed: - Number of standard ITNs - Number of PBO ITNs - Number of Dual a.i. ITNs (specify) - Number of other ITNs (specify) |  |
| Dates planned for microplanning |  |
| Dates planned for household registration (HHR) |  |
| Dates planned for ITN distribution |  |

(ii) Map of country

- Where available, include a map of the country showing areas targeted and ITN types planned for distribution (copy from campaign PoA).

(iii) Purpose of the DPoA

- Include one to two paragraphs describing the purpose of the digitalization plan of action. For example:

  - Provide background information on the need for digitalization.

  - Define the campaign components and processes to be digitalized.

  - Provide information on the digitalization strategy including selection of platforms, mobile devices, and outlining security protocols.

  - Provide information on planning and coordination mechanisms including roles and responsibilities of partners and committees involved in the campaign.

  - Identify potential risks and outline strategies to mitigate them proactively.

  - Provide information on technical support and training needs for the implementation of the campaign.

(iv) Accompanying documents

Brief section (1 paragraph) listing the materials accompanying the DPoA:

- Detailed digitalization timeline (Excel). Example: Annex 1

- Detailed digitalization budget (Excel). Example: Annex 2

- Terms of reference (TOR) for Digitalization Sub-committees at all levels planned. Example: Annex 3

- TOR for digitalization/ICT4D positions (national/international consultant, IT supervisor and technical assistant). Example: Annex 4

- Macro positioning and storage plans (Excel)

- Mobile devices distribution  (Excel). Example : Annex 5

- Warehouse assessment checklist (Excel). Example: Annex 6

- Risk assessment and mitigation plan (see example) (if digitalization risks are not included in the overall campaign risk assessment plan or if the digitalization Sub-committee will monitor and update the digitalization-specific risks during the planning and implementation period).

2. National digitalization landscape and context

(i) National context for digitalization

(This can be taken from the Campaign digitalization matrix if used prior to developing the DPoA.)

- Describe the national digitalization landscape, including whether there are policies or regulations in place for collection and management of personal data, existing frameworks for digitalization, government departments dedicated to digitalization or data, national strategies and policies for establishment and use of geo-repositories, etc.

- Describe any other health campaigns, e.g. immunization, neglected tropical diseases, etc. that digitalize any part of their campaigns and how the lessons learned from those campaigns can feed into digitalization planning.

- Describe the digitalization context for the campaign, including all information that influences planning and implementation of campaign digitalization, e.g. mobile network infrastructure, access to electricity, Internet access and usage, mobile payment service, hard-to-reach and/or insecure areas, etc. (This can be taken from the Campaign digitalization matrix if used prior to developing the DPoA.)

- Digitalization key indicators (use the results of the Campaign digitalization matrix to fill this table).

Table XX: Key indicators

| Labels | Indicator/figure |
| --- | --- |
| National information health system platform |  |
| Major mobile companies |  |
| Mobile users |  |
| Internet users |  |
| Mobile penetration rate |  |
| Internet penetration rate |  |
| 2G coverage rate |  |
| 3G coverage rate |  |
| 4G coverage rate |  |
| Access to electricity |  |
| Social media users |  |
| Main used social media platform |  |
| Main device used to browse the Internet |  |
| Etc. Add other indicators as applicable/available |  |

ii. Digitalization lessons learned from previous campaign(s) or other experiences and recommendations for current campaign

(This section could also be attached as an annex depending on the length. It should be used to inform digitalization improvements or decisions for the current campaign.)

Provide a summary in table format (see example) of the digitalization lessons learned from efforts made to date by the national malaria programme for routine, campaign or survey data collection. Based on these lessons learned, describe the recommendations for the current campaign and how the challenge or lesson learned will be addressed. NOTE: the timeline should add more precision regarding who is responsible for ensuring the recommendations are planned and implemented correctly.

Table XX: Lessons learned from previous campaign(s) (examples)

(The Campaign digitalization matrix should provide useful information here.)

| Campaign area | Challenge, lesson or recommendation | Specific detail related to challenge, lesson or recommendation | Plans for current campaign |
| --- | --- | --- | --- |
| Digitalization planning | Late decision-making. | Planning and decision-making took place late, which delayed procurement and the overall campaign implementation. | Planning for the digitalization will begin at least 12 months before the planned distribution date and key decisions will be taken 10 months before the planned distribution date. |
| Coordination | Strong coordination of partners is critical for ensuring standardization throughout the country. |  | Reinforce coordination structures at all levels, ensuring all partners are engaged and actively supporting the campaign. |
| Quantification | Quantification of health products is a major challenge. Population figures from census projections are often inaccurate and average household sizes smaller than predicted. | Inaccuracies lead to ITN shortages. | Use of geospatial mapping during microplanning should improve accuracy of projections. |
| Microplanning | There are many hard-to-reach areas that require specific planning to ensure that all targeted populations are reached. |  | Ensure microplanning tools and training are adjusted to incorporate specific planning for hard-to-reach areas specific to digitalization. Ensure decisions can be taken early for areas where the deployment of digital data collection may be problematic. |

Add one or two paragraphs detailing any other campaign issues that will affect digitalization planning or create new digitalization challenges and that need to be considered during the planning for the upcoming campaign. This may include, for example, adaptations to supply chain digitalization for improved traceability of ITNs.

iii. Objectives and scope of the campaign digitalization

Provide the purpose of the digitalization. Examples include but are not limited to the following:

- Efficient household mapping and allocation of campaign resources using geospatial data.

- Identification of households using geospatial maps to ensure no missed households or settlements to improve universal coverage of ITNs through virtual campaign monitoring and supervision.

- Digital tracking of training attendance for participation evaluation and generation of digital attendance sheets to ease payment processing.

- Real time tracking of campaign workers and ITNs distributed from storage to recipients to improve accountability.

- Real time data for analysis to inform immediate corrections where necessary.

- Use of digital communication services like SMS notifications to disseminate key malaria messages.

Provide the digitalization objectives in support of achieving the overall campaign objectives. Note: Ensure that the objectives have quantified and measurable targets (e.g. 100 per cent of electronic payments are transferred in a timely manner to recipients).

Note: The campaign digitalization indicators, which should be included in a table in the campaign PoA or the M&E PoA if it is a separate document, should align with the overall digitalization goal and objectives. They can be taken from the Campaign digitalization matrix if used prior to developing the DPoA).

3.   Overall digitalization strategy

Describe the overall digitalization strategy for the campaign:

(i) Platforms and apps selection

(Use the Campaign digitalization matrix to inform this section.)

- Describe the platform that will be used and the reasons for the selection of the platform for the campaign.

- Describe how the selected platform is set up, whether on a local server/data centre or cloud, and key features (processor, memory, storage, operating system).

- List any license acquisition needed for specific software.

- If there is more than one platform to be used, describe the functions attributed to each of them, and how they will be interoperable to allow the flow of data between them. Describe which of the platforms will aggregate all the collected data and where data will be housed at the end of the campaign.

- Describe the devices that will be used for data collection for different campaign processes.

- Describe the app(s) that will be installed on the devices for data collection at the field level (including functionality, such as offline capability).

- Describe the levels at which data will be collected and how the data will be synchronized or entered into the server and stored into the digitalization platform (insert a diagram of the data flow from the field to the server).

(ii) IT infrastructure and policy

- Describe the policy in place in term of data security, physical access to server or storage, user pre-defined access rights, back-up of data and any relevant information related to data security and integrity.

- Describe any weaknesses from the country landscape key indicators that may hinder some aspects of the campaign digitalization (e.g. no data network coverage map in some locations and no near spots to synchronize). This can be added into the digitalization risk and mitigation plan.

- List the communication means (e.g. letter) to be addressed to any functional entity, institution, structure already in place that can support aspects of the campaign digitalization (e.g. national GIS institution for maps, Health Information System unit at the MoH level, government data centre, etc.).

(iii) Hardware management and storage

- If Mobile Device Management (MDM) is planned, describe the process of acquiring the necessary software/external organization that will run it.

- Describe the storage and transport (including secure packaging) of digital devices such as tablets/smartphones, power banks, etc. throughout the in-country supply chain, including roles and responsibilities for the equipment and inventory at each level. Describe any specific logistics requirements if, for instance, some of the devices are community-owned.

- If applicable, describe the storage and transport of equipment for digitalization in a scenario where the campaign will be in phases and digitalization equipment must be moved from one location to another, including roles and responsibilities at each level.

- Since digitalization devices are valuable commodities, describe the security arrangements at warehouses or any other storage location to ensure the safety of the digitalization tools and equipment.

- Describe any tracking document for digitalization equipment at each level, e.g. dispatch to household registration personnel and collection back into storage location.

- Describe the membership and function of reception committees at each level (as applicable).

- Describe the procedures by which apps or software used during the campaign will be wiped from the equipment once the campaign is complete and information archived.

- Describe the criteria and procedures for reverse logistics at the end of distribution period (e.g. how, when and where to reverse). If on loan, describe how equipment will be checked, repaired if necessary and returned to the owner.

(iv) Quantification of campaign personnel and mobile devices

- Describe the strategy for the acquisition of the devices (e.g. smartphones, tablets) that will be used in digitalizing the campaign (e.g. will they be procured, will they be community-owned (Bring Your Own Device – BYOD), will it be a hybrid approach?).

- If community-owned, what are the minimum technical requirements for smartphones/tablets?

- If BYOD what are the steps for mobilizing the devices, security of the data, etc.?

- If a hybrid approach is used, describe how mapping will be done to allocate procured devices versus where community-owned devices would be mobilized

(v) Digitalization quantification and macro logistics

- Macro-quantification should be described for devices and power banks, including whether a contingency stock will be procured (and the percentage if so). The quantification each piece of equipment (e.g. devices, power banks, etc.) per health district and per cadre of campaign personnel should be based on the digitalization strategy.

- Describe and quantify digitalization equipment that can be borrowed by the national malaria programme from any third party (e.g. equipment pool from MoH, other health department, etc.) and the procedures and agreements needed (including who will be responsible). Ensure this is included in the digitalization timeline.

- Macro-quantification should be described for any other major items that will be procured, such as digitalization equipment (platform) and vouchers, including the quantification base used for estimates and whether a contingency stock was procured (and the percentage if so).

(vi) Digitalization procurement and delivery (macro logistics)

- Describe who is responsible for management of the digitalization procurement process (e.g. entity responsible at country level and whether procurement will be done locally or from external supplier, or through a third party) and provide information on procurement lead times and/or delivery timelines.

- Provide a table (see example below) of the digitalization equipment specifications for each type of device, whether tablets, smartphones, power banks, mifi, server, routers, etc. procured, as well as the quantity.

Table XX: Specifications of digitalization equipment

| Equipment | Specifications | Accessories | Quantity | Donor/Procurement partner |
| --- | --- | --- | --- | --- |
| Tablet | Brand, OS, CPU, memory, camera, GPS, battery, dimension | Charger, cable, adapter, screen protector, protective case |  |  |
| Power bank | Brand, battery capacity | Charger, cable, adapter |  |  |
| Server | Brand, OS, CPU, memory, back-up |  |  |  |
| Software (proprietary software) | OS, virtualization, backup, online storage, etc. |  |  |  |
| Storage and transport case for handled devices | Hard-shell case, dimension, lockable |  |  |  |
| Mifi | Network coverage, speed, sim card slot, | Charger, cable, adapter |  |  |

- Describe where the digitalization equipment will be delivered on arrival (e.g. central, region, district levels).

- Describe at what level the transfer of responsibility takes place from the procurement agent to the in-country partner (e.g. the national malaria programme or a different organization), as well as to service providers or other logistics partners as applicable throughout the levels of the device/equipment supply chain.

- Develop a template  to track delivery and return (reverse logistics) of devices at all levels.

(vii) Other equipment, tools, services and materials procurement and delivery (macro logistics)

This includes equipment, tools, services and materials for campaign digitalization-related activities including all the different services and items required to ensure success, for example:

- Training, workshops, orientations – venues, generators or projection equipment, catering services, training materials such as notebooks, pens, etc.

- Data packages or airtime for communication for all household registration and ITN distribution personnel and other personnel (supply chain, supervision, monitoring) as applicable.

- Supervision and monitoring, payment implementation and oversight – rental of vehicles, purchase of fuel, vehicle maintenance, etc.

4. Planning and coordination of campaign digitalization

(i) Digitalization coordination mechanism

- Describe the process to be used to  gather requirements and define the workflows to be digitalized.

- Describe the membership and function of the digitalization Sub-committee, and origin of representatives (e.g. national malaria programme, government M&E and health systems information departments, national consultant(s), etc.). Add the frequency of meetings.

(ii) Responsibilities of the digitalization Sub-committees

- Annex the terms of reference (TOR) for the digitalization Sub-committees at lower levels (if not already done so in Section 1).

- Describe the roles and responsibilities of the sub-national coordination structures and digitalization personnel at each level.

(iii) Roles and responsibilities of digitalization partners

- Describe the key digitalization partners that will be involved in the campaign. The description should explain their roles and responsibilities. This may also be done in the form of a table (see below).

- Describe any functional entity, institution, structure already in place that can support aspects of the campaign digitalization (e.g. national GIS institution for maps, Health Information System unit at the MoH level, government data centre, etc.).

- Describe outsourced services that will be needed from a third party to complete some aspects of the digitalization activities.

- Describe the implementation arrangements for the campaign, including any activities that will be outsourced to third parties (such as set-up of the data platform or electronic payments).

Table XX: Partners, roles and responsibilities

| Partners | Functional roles and responsibilities |
| --- | --- |
| National malaria programme | Coordinate with partners involved in the digitalization of the campaign and validate decisions related to any aspect of the digitalization plan, including platform and device specifications, on advice from the Digitalization Sub-committee. Liaise with national statistics bureau and other government departments and ministries as appropriate. Lead the process for borrowing of devices as applicable. |
| Campaign funding partner(s) | Funding for the digitalized components of the campaign, including procurement of devices. |
| Technical partners | Support configuration, platform set-up, technical oversight, training and capacity-building, overall management of the digital platform, data visualization, troubleshooting during implementation. |
| Telecommunications company | Provide the telecom network and services for mass SMS related to SBC activities, electronic payments to campaign staff and data connectivity and mapping of cell hotspots countrywide. |

5.	Implementation and technical support

(i) Data collection and management during HHR/ITN distribution

- Describe the key steps for campaign digitalization during the ITN campaign, including:

  - Daily set-up/organization.

  - Daily check and handover note of equipment to HHR/ITN distribution teams.

  - Daily review at the end of the day, recharge of equipment and readiness for the following day.

- Describe how data will be collected for the selected strategy (e.g. one or two phase) for household registration and ITN distribution (e.g. door-to-door, fixed distribution points, strategy for special populations and internally displaced people and refugees, etc.) differentiated by urban and rural as applicable.

- Provide information on how the households will be marked as having been registered (voucher, QR code, etc.).

- Describe how the data collected will appear, i.e. as aggregate data with data entry done at the district level into the system or from the individual household data transmitted to the remote server directly.

- Describe who will be responsible for campaign digitalization accountability during the distribution (e.g. the distribution point supervisor or a community supervisor for door-to-door distribution) and their roles and responsibilities, including for rural and urban areas.

- If vouchers or a QR code were included for household identification during the registration phase, describe how they will be managed during the registration and distribution processes.

- Briefly describe how the data collected will be summarized each day, transmitted, shared and used for action during the ITN distribution.

(ii) Data management, reconciliation and feedback systems

- Describe the roles and responsibilities for campaign digitalization data collection and management at all levels.

- Describe how data will be collected (through digital data collection tools or a hybrid model.) NOTE: Adapt sections above and below based on the system being used.

- Describe the data transmission flow, indicating whether the data are collected at the lowest level (household) using digital collection tools or whether data entry takes place at the district level, based on paper forms collected  from lower levels. Specify the expected timelines for data submission in each scenario, including any adapted timelines for hard-to-reach areas. Describe the feedback system that will be put in place to ensure data-driven decision-making during the campaign. Include how feedback will be shared with field teams and all levels of the system, for example through WhatsApp groups or other communication platforms.

- Describe how data from supervision and/or monitoring checklists will inform decision-making about quality of the digitalization process and how it can be improved.

- Describe how the digitalization process can help programmatic and logistics data to be triangulated during and post ITN distribution.

- Describe how the campaign will be closed (e.g. which data are required to ensure that campaign objectives and programmatic and financial requirements are met before ITNs remaining are redeployed for distribution through routine or continuous distribution channels or for storage at a higher level of the supply chain).

(iii) Incidents and technical support

- Describe how campaign personnel will get support in case of incidents or problems (e.g. any plans for technical personnel in the field).

- Describe the support staff profile at each level of support (central, district, sub-district).

- Describe the process of reporting any incidents or issues (e.g. problem, loss or damage of equipment) that need attention during implementation, including the communication channel(s) that will be used.

- Describe the helpdesk and how it will function, as well as who is responsible for ensuring its continuous operation during activity implementation.

(iv) Supervision and monitoring

- Describe the key digitalization activities that will be supervised and monitored (e.g. storage and dispatch of equipment, HHR and distribution etc.)

- Describe the daily supervisory activities that ensure digitalization staff are in place at their assigned locations (e.g. supervisor report, handover note, data entry and GPS tracking etc.).

- Describe how the MDM software and the disaggregated flow of data coming in will help to supervise and monitor the effectiveness of digitalization staff work in real time using both visualization and remote support, as well as targeted in-person support.

(v) Accountability of devices, tools and materials

- Describe the tools and procedures that will be used to ensure accountability for digitalization equipment received for the campaign throughout the supply chain, including during the reverse logistics process.

- Describe how to handle any loss of digitalization equipment and the way to address the issue in a formal manner (complaint to the community leaders, police, etc.).

- Describe how the SOPs for handover of equipment to any staff will ensure the receiver is accountable for any damage or loss by negligence.

NOTE: Tracking procedures and tools should be the same for all materials, (i.e. waybill, stock sheet, tally sheet, inventory), in order to simplify both the supply of the tools and the training required to use them.

Tracking tools should be annexed, including detailed SOPs on how to use them.

(vi) Security and incident management

- Describe the measures that will be implemented to safeguard digitalization equipment during transport, storage and use at all levels (e.g. asset tagging, custody logs, secure storage, access controls, mobile device management etc.).

- Outline the incident management process for lost, stolen, or damaged devices (and any related incidents), including reporting channels, timelines, verification and documentation procedures, responsibility for follow-up, and arrangements for repair or replacement.

- Training and capacity-building

(i) Recruitment and training of campaign digitalization personnel

- Describe the professional profiles required for the campaign digitalization

(e.g. national/international digitalization consultant, software developers, IT support staff, IT supervisors at district level, data managers, etc.).

- Describe the digitalization human resources structure (e.g. national consultant, IT support) that will be put in place at each level to support implementation.

- Describe the preparatory steps that will take place in advance of all campaign digitalization training sessions including:

  - Preparation of training venues and equipment (projectors, devices, connectivity).

  - Configuration of devices and user accounts in advance.

  - Set-up and testing of virtual training platforms (e.g. Zoom, Teams, national e-learning platforms) where remote or hybrid trainings are planned.

- Describe the development of training-specific agendas, tools and materials (e.g. SOPs, user guides, checklists, demonstration environments) to ensure that training is well-targeted to the roles at each level. Indicate how materials will be adapted for:

  - In-person, hands-on sessions.

  - Virtual or hybrid sessions (shorter modules, screen-sharing demonstrations, recorded tutorials).

- Describe the production of materials including where materials will be developed and how they will be bundled and transported to training levels.

- Describe the selection of campaign digitalization personnel based on criteria established (e.g. those undertaking training of trainers with IT educated background, registration/distribution personnel with good experience with technology and the use of electronic devices).

- Summarize the campaign digitalization trainings that will occur at each level (central, regional, district, sub-district, health facility, community) in a table, and clearly describe the training format for each level:

  - Fully in-person.

  - Virtual (e.g. national-level orientation via video conference).

  - Hybrid (e.g. central virtual sessions combined with in-person district practice sessions).

(ii) Digitalization training plan

- Describe the training methodology, as well as key tools for campaign digitalization that will be introduced and used (e.g. SOPs, tracking tools, etc.). Explain how sessions will be organized that allow for practice with campaign digitalization tools.

- Explain how evaluation of the training sessions will take place, both for the overall training organization and quality and for the capacity assessment of trainees at the end of the sessions.

- Explain where all training materials will be stored to ensure access by all partners (e.g. Google Drive, Dropbox, etc.).

Note: Internet connectivity constraints should be considered when deciding where virtual or hybrid trainings are feasible. Connectivity mapping during microplanning should identify:

- Levels where virtual/hybrid modalities are realistic (e.g. national, regional, selected districts).

- Levels where training must remain fully in-person due to poor connectivity, with offline copies of digital training materials provided on devices or storage media.

Table XX: Digitalization training plan

| Level | Type of training | Objective of training | Participants | Facilitators | No. days |
| --- | --- | --- | --- | --- | --- |
| Central | Training of trainers, supervisors for campaign digitalization activities | Equip participants with the skills and knowledge for management of the campaign digitalization aspects, including: - Knowledge of the SOPs to be followed by household registration and ITN distribution personnel in their daily activities - The use of tablets and questionnaires for the household registration - Knowledge of the SOPs concerned with reporting issues - Knowledge of the support available, including helpdesk, etc. - Knowledge of the checklist related to known issues that personnel in the field can refer to before seeking helpdesk support | IT/ICT4D recruited staff to support the campaign digitalization | Chair of the campaign Digitalization Sub-committee, with support from national or international digitalization consultant. Health Information System personnel from MoH. | Four or less depending on digitalization experience and familiarity |
| Health facility | Training addressed to field personnel | To ensure familiarity with campaign digitalization SOPs, the proper use of the tablets and questionnaires and how to report issues and seek support when needed. | Maximum of 20 people per session | Trained trainers, supervisors | Two |

- Configuration, test and validation of digitalization platform and tools – pilot

(i) Pretesting of the digital devices and software/user acceptance test (UAT)

- Define the purpose of the UAT (typically to ensure that the software and hardware meet all the requirements and function as expected before being deployed in the field).

- Specify the components to be tested (e.g. servers, mobile devices (phones and tablets), chargers and SIM cards, software configurations, application features, performance indicators, household registration forms, visualization and dashboard updates, connectivity, QR and/or barcode scanning capabilities).

- Define the testing procedure (software testing, hardware testing, connectivity testing and configuration validation).

- Compile a brief report detailing the testing process, results and any issues found, highlighting the recommendations for improvements or necessary changes.

- Define the process for a post-deployment review to address any issues that arise in the field.

(ii) Pilot of the digitalization process and application

- Clearly state the purpose and goals of the pilot test.

- Identify all components to be tested, including infrastructure, software, hardware and campaign process.

- Describe what needs to be set up prior to the deployment of the platform (local or online server, capacity, government/private data centre, bandwidth requirement, back-up, security, etc.).

- Describe how the selected platform will be configured to accommodate the aspects of the campaign that will be digitalized.

- Describe how specific modules will be developed in digitalized format from paper-based tools, dashboards etc., related to the aspects of the campaign that will be digitalized.

- List the requirements for pre-testing and validation of each piece of software (app(s), indicators, questionnaire(s), dashboard, configuration, updates, etc.), hardware (equipment, server, tablet, tools, charger, SIM card, power bank, etc.) and service (connectivity, QR scan, data package, SMS, printing, etc.).

- Describe how the pilot will use worst case scenario situations such as no connectivity, loss of equipment, dysfunctional power bank, frozen tablet, blurred screen, failed scans, etc.

- List the already known issues for which campaign field personnel can find a work-around solution.

- Define the process for a post-pilot review to address and correct any issues that arise during the pilot.

8. Digitalization risk assessment and mitigation (from the Risk assessment and mitigation plan)

- Provide a brief summary of the key risks during the campaign digitalization operation (e.g. rainy season, damage to equipment, connectivity issue, synchronization issue, insecurity during transportation and warehousing, traffic, especially in urban areas, accessibility, theft, etc.) and mitigation measures.

- Refer to the sample risk and possible mitigation measures for digitalization of ITN mass distribution.

NOTE: the risk assessment and mitigation plan is a living document as risks will change over the period that the campaign is planned and implemented. The plan should be developed in Excel or Word as an annex to the DPoA to allow it to be regularly updated. It should not be included as a table or figure in the DPoA as the plan will constantly evolve.

- Post-distribution digitalization activities

Describe any post-distribution activities, including:

- Final data reconciliation and validation through review meetings (describe which levels will have review meetings, who will participate, key expected outcomes and number of days at each level).

- Archiving, back-up of campaign data to a secure server, storage instance, ideally on a government-owned server and national information health system.

- Management of software library to store any acquired licenses through the campaign digitalization process.

- Reverse logistics for digitalization equipment and tools, including the time during which the operation should be complete and to where the equipment will be transported.

- Sign-off of final inventory of digitalization equipment by approved authority attesting the condition of the equipment.

- Sign-off of list of damaged or lost equipment and any specific pending issue(s) that needs follow-up.

10. Documentation, reporting and follow-up

- Describe how information will be collected to inform the final digitalization report to collect lessons learned and recommendations for future campaigns, for example:

  - Reports from various digitalization supervisors and monitors at all levels.

  - Supply data summarizing key figures of the digitalization service provided (number of helpdesk queries solved, number of pending issues, etc.). This can be taken from dashboards if applicable.

  - Collection of information from decentralized campaign personnel through online questionnaires, key informant interviews, focus group discussions or other methods.

- Describe how the final campaign report will be developed, validated and disseminated, including to whom, as well as how lessons learned will be used. Describe any plans for evaluation of the digitalization aspects of the campaign and how the evaluation results will be used.

Annexes

- Results of decision-making from the Campaign digitalization matrix

- Detailed digitalization timeline (Excel) (See Annex 1)

- Detailed digitalization budget (Excel) (See Annex 2)

- Terms of reference (TOR) for digitalization Sub-committee (Annex 3)

- TOR for national digitalization consultants, supervisors, technical assistants (Annex 4)

- Mobile device distribution sheet (Annex 5)

- Warehouse assessment checklist for digital devices (Annex 6)

- Risk assessment and mitigation plan (Excel, regularly updated)

- SOPs developed for all aspects of digitalization (e.g. household registration, ITN distribution, logistics, supervision, payments, etc.)

- Quantification of materials to be procured (Excel)

AMP resources

- ITN campaign digitalization matrix

  - Planning and budgeting checklist

  - Risk register

- Digitalizing malaria campaigns: ITN and SMC handbook.

- Digital tools for health campaigns.

- Deploying digital tools in ITN campaigns – risks and mitigating measures.

- The use of digital tools to improve the operational efficiency of ITN campaigns.

- Annex to above: Feature table. The use of digital tools.

- Survey on digital tools for an ITN mass campaign: analysis and report.

- ITN geo-enabled resources for microplanning.

- Online data collection for process evaluation of a mass ITN campaign distribution.

- Recommendations for minimum data requirements for household registration and ITN distribution.

- Using electronic payments in ITN campaigns.

- Planning the use of barcode scanning for the ITN supply chain at the country level.

- SOPS to accompany above. Automatic Identification and Data Capture (AIDC) for ITN supply chain programming

- Alternative to vouchers for ITN distribution in a digitalized campaign.

- ITN distribution operations: considerations for optimizing limited resources.

https://allianceformalariaprevention.com/resource-library/resource/itn-campaign-digitalization-matrix/

MDM is the process of managing mobile devices in terms of usage and security. Essential information about each device is tracked including if they are lost or stolen. For example, it is possible to track a device by its geographical location.

See AMP toolkit, Chapter 5, Brief 6, Management of the supply chain. https://allianceformalariaprevention.com/resources/amp-toolkit/toolkit-2-0/