## Feuil1
#VALUE!
Annex: Example of part of a risk assessment and mitigation plan
Campaign area | Risk | Detail of risk | Likelihood | Impact | Heat map | Mitigation plan | Risk owner | Timing for addressing risk
Quantification | Insufficient ITNs available for single-phase distribution | ITNs are insufficient to cover the targeted households because updated needs from household registration are not available in advance of ITN distribution (e.g. pre-positioning based on microplanning figures) | 3 Possible | 4 Significant |  | Pre-position contingency stock (if available) at district or regional level for deployment as needed based on data during implementation. If no contingency stock available, consider capping the number of ITNs per household either prior to or during the implementation of the registration or distribution based on data received. | MoH (NMCP) | During planning and implementation of the distribution
ITN storage at community level | insufficient secure pre-positioning sites (PPS) to facilitate resupply of door-to-door distribution teams | Many PPS are required to avoid a need to resupply ITNs to teams with other means such as motorcycles or tricycles. In some targeted areas, it may not be possible to find the required number of PPS that meet the minimum criteria for security. | 2 Likely | 3 Moderate |  | Early identification of areas with problems during microplanning. Where storage exists but security is the issue, plan for local security to reinforce any existing measures in place. Where no storage exists, determine alternate means for resupply of teams. | MoH (NMCP) | Verification of storage gaps at community level immediately after microplanning consolidation and validation
Resupply of door-to-door ITN distribution teams | Difficulties in quantifying and ensuring sufficient resources for regular resupply of door-to-door ITN distribution teams | Teams may move more slowly or quickly than planned, making the timing and frequency of resupply difficult to establish. Urban areas add additional complexity with traffic and other conditions. Risk of delayed distribution to households if the resupply cannot be planned in a timely manner. Financial implications of extending days of distribution. | 3 Possible | 4 Significant |  | Identify PPS as close as possible to door-to-door teams to reduce the need for resupply of ITNs. Monitor implementation of the resupply on the initial distribution days and make adjustments as needed – ensure contingency funding is available in the budget after microplanning. | MoH (NMCP) | After microplanning consolidation and validation and during implementation
Waste management of ITN packaging | Possibility of residual chemicals from the ITNs adhering to plastic materials used to package ITNs being spread into the environment. | Individual ITN packaging, bales, baling material, strapping and other plastic wrapping, all have the potential to harm campaign personnel | 2 Likely | 3 Moderate |  | Develop a waste management plan to gather and dispose of all campaign waste. Follow national government guidance for disposal and ensure that microplanning includes mapping of appropriate waste management facilities. | MoH NMCP | During macroplanning and quantification for the distribution, as well as during microplanning
Supervision | Inadequate monitoring and supervision | Insufficient trained personnel at implementation level | 2 Likely | 3 Moderate |  | Adapt monitoring and supervision of ITN campaign activities as far as possible to make virtual | MoH (NMCP) | During macroplanning and implementation of activities
Payments | Delayed personnel payment | Inadequate verification of account details Payment agency not able to operate at local level | 2 Likely | 3 Moderate |  | Plan for early submission and verification of personnel lists and account details. Plan for timely submission of payment justifications. Ensure regular follow up. Include payment related milestones in the campaign timeline. | MoH (NMCP) | During macroplanning, microplanning and implementation of activities
Key
Likelihood | Impact |  | Risk | Heat colour
1 Unlikely | 1 Negligible |  | Negligible
2 Likely | 2 Insignificant |  | Low
3 Possible | 3 Moderate |  | Moderate
4 Almost certain | 4 Significant |  | High
Likelihood | Negligible | Insignificant | Moderate | Significant
1 Unlikely
2 Likely
3 Possible
4 Almost certain