## Timeline
Activities timeline - Digitalization distribution campaign - ADAPTABLE TOOL
ID | Activity | Comments | Responsible/sub-committee | 10-12 months before Distribution | Suggested timing (from distribution month)
[5 empty] | 10 months before distribution |  |  |  | 9 months before distribution |  |  |  | 8 months before distribution |  |  |  | 7 months before distribution |  |  |  | 6 months before distribution |  |  |  | 5 months before distribution |  |  |  | 4 months before distribution |  |  |  | 3 months before distribution |  |  |  | 2 months before distribution |  |  |  | 1 month before distribution |  |  |  | LLIN distribution month |  |  |  | 1 month after distribution |  |  |  | 2 months after distribution |  |  |  | 3 months after distribution |  |  |  | +4 months after distribution
[5 empty] | W 1 | W 2 | W 3 | W 4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Establish campaign technical/ICT sub-committee
1 | Decision-making on digitalization based on context, operational needs, risk etc (Campaign digitalization matrix) | Ensure enough time and knowledgeable people to respond to the questionnaire. Identify and invite key partners from relevant departments, agencies and partner organizations to participate in sub-committee. | MoH/NMP/Partners
2 | Landscape assessment on the country digitalization readiness, tool, logistics etc. | Collect information related to key in-country digital indicators | MoH/NMP/Partners
4 | Set up Digitalization sub-committee to manage the campaign digitalization | Ensure ToR and responsibilities of the Digitalization sub-committee | MoH/NMP/Partners
5 | Decisions on campaign components that need to be digitalized | Collect as much information as possible for the context analysis and operational needs. Use the AMP Digitalization matrix: https://allianceformalariaprevention.com/resource-library/resource/itn-campaign-digitalization-matrix/ | MoH/NMP/Partners | bar: 10 months before distribution W 1 to 10 months before distribution W 4
6 | Selection of campaign digitalization platform or tool to be used | Information collected from the matrix will help select components to be digitalized and the software platform to support the digitalization | MoH/NMP/Partners | bar: 10 months before distribution W 1 to 10 months before distribution W 4
7 | Generate a list of any other related software, hardware and infrastructure to set up (device management system (MDM), accessories, server) | Response from the matrix will help select additional related software/hardware | Digitalization sub-committee | bar: 10 months before distribution W 4 to 9 months before distribution W4
8 | Identify technical expertise to manage or support the digitalization | Response from the matrix and platform selected will help identify the HR expertise needed for the digitalization. This could be from the MoH, NMCP etc. | Digitalization sub-committee | bar: 10 months before distribution W 4 to 9 months before distribution W4
9 | Assess in-country available infrastructure to support the digitalization vs. what will be needed to complement the local resources | What resources can be found in-country and what will need to be outsourced? | Digitalization sub-committee | bar: 10 months before distribution W 4 to 8 months before distribution W1
Recruit/mobilize ICT4D team | bar: 10 months before distribution W 4 to 9 months before distribution W4
10 | Develop a staffing plan and related ToRs (Digitalization HR plan) | Mobilize/recruit technical experts (such as members of the ICT4D team or external consultants) as per the policies/protocols of the funding or NMP partners | Digitalization sub-committee | bar: 9 months before distribution W2 to 8 months before distribution W4
11 | Procurement, storage and transport
12 | Quantification of devices including devices and accessories (tablets, powerbank etc.). Establish a list of device requirements by regions, provinces etc. | A comprehensive list of devices per region, province and district that can be fine tuned later on | Digitalization sub-committee/Logistics sub-committee | bar: 10 months before distribution W 1 to 8 months before distribution W4
13 | Procurement of devices and accessories either within the country or offshore (international procurement) | Start working on quantification to give enough time if the devices need to be procured from abroad | Digitalization sub-committee/Logistics sub-committee | bar: 10 months before distribution W 1 to 8 months before distribution W4
14 | Issue validated tender for tablets, power bank and accessories procurement, including strict evaluation criteria and deadlines |  | Digitalization sub-committee/Logistics sub-committee | bar: 10 months before distribution W 1 to 8 months before distribution W4
15 | Select clearing agent and sign contracts (through tenders) | Ensure open and transparent process to avoid incurring delays within the campaign timeline | Digitalization sub-committee/Logistics sub-committee | bar: 10 months before distribution W 1 to 7 months before distribution W1
16 | Develop a calendar for tablets, power bank arrival and monitor the pipeline of shipping and delivery |  | Digitalization sub-committee/Logistics sub-committee | bar: 10 months before distribution W 1 to 4 months before distribution W4
17 | Establish digitalization equipment storage and transport at different levels, HQ, provinces, districts etc. | Ensure a proper storage plan and transport | Digitalization sub-committee/Logistics sub-committee | bar: 10 months before distribution W 1 to 4 months before distribution W4
DPoA development and meetings
18 | Draft of the DPoA - align with the campaign strategy during macroplanning | Draft 0 of the DPoA | Digitalization sub-committee | bar: 10 months before distribution W 1
19 | Risk and mitigation plan | Draft 0 of the Risk and mitigation plan | bar: 10 months before distribution W 3 to 9 months before distribution W4
20 | Establish a draft timeline of digitalization with priority activities | A timeline with the activities that need attention and consideration. Ensure that the timeline of the digitalization is aligned with the global timeline of the campaign with key milestones specific to digitalization process | Digitalization sub-committee | bar: 10 months before distribution W 3 to 9 months before distribution W4
21 | Final DPoA document | The subcommittee (with support from the ICT4D team) should develop a detailed digitalization plan of action (PoA), or digitalization section in the PoA, clearly explaining the different components of the digitalization strategy, as well as a detailed quantification (based on decisions on which activities should be digitalized) and budget | Digitalization sub-committee | bar: 10 months before distribution W 3 to 6 months before distribution W4
22 | Convene regular sub-committee meetings with stakeholders | (1) Review the campaign components and the possible challenges; (2) Revisit the "Campaign digitalization matrix" and make any adjustments necessary; 3) Identify the objectives for digitalization; (4) Identify the different digital platforms that can meet these objectives; (5) Discuss the pros and cons/limitations of each of the tools; (6) Decide which campaign activities should be digitalized. | Digitalization sub-committee | bar: 10 months before distribution W 1 to 1 month before distribution W4
23 | Update the digitalization risk and mitigation plan and keep as a living document | Keep updating the document over time. Ensure that it is aligned with the global risk and mitigation plan for the campaign | Digitalization sub-committee | bar: 10 months before distribution W 3 to 4 months before distribution W4
Digitalization setup, tools development, pre-test and pilot
24 | Gather requirements on the campaign components to be digitalized and details of the processes |  | Digitalization sub-committee | bar: 10 months before distribution W 3 to 8 months before distribution W4
25 | Configuration of servers (Cloud or on-premise infrastructure) | This should be done according to platform selected | Digit support team/HMIS/Digit Partner | bar: 10 months before distribution W 3 to 4 months before distribution W4
26 | Configuration and customization of the digital platform or tool | In liaison with Log. and SBC start the digitalization of the forms and questionnaire into the platform. Ensure that all forms related to stages of the campaign planned to be digitalized are integrated into the selected platform | Digit support team/HMIS/Digit Partner | bar: 10 months before distribution W 3 to 4 months before distribution W4
27 | Specific digitalization requirements if any | Make sure the specific requirement from a given partner is taken into consideration when developing the tools. Moreover, standard operations procedures (SOPs) must be in place to allow everyone involved to comply on all digitalization requirements | Digitalization sub-committee | bar: 10 months before distribution W 3 to 4 months before distribution W4
28 | Plan for pilot of the campaign digitalization |  | Digitalization sub-committee | bar: 5 months before distribution W1 to 4 months before distribution W4
29 | Pre-test and validation test to prepare for the pilot | Test and validate the questionnaire by users (UAT) | Digitalization sub-committee | bar: 5 months before distribution W1 to 4 months before distribution W4
30 | Configuration of the devices for the pilot | Given the number of tablets to be configured, recruit enough staff | Digitalization sub-committee | bar: 10 months before distribution W 3 to 4 months before distribution W4
31 | Campaign digitalization pilot | To be aligned with the campaign overall pilot | Digitalization sub-committee | bar: 10 months before distribution W 3 to 4 months before distribution W4
32 | Lessons learned from the pilot and necessary correction measure to improve the digitalization when scaling up | Equipment and related digitalization operations and services should be stressed in various case scenarios taking into account the campaign strategy for household registration (HHR) and distribution and also mobile network coverage | Digitalization sub-committee | bar: 10 months before distribution W 3 to 4 months before distribution W4
33 | Digitalization trainings
34 | Training to digitalization staff in cascade from the HQ to the HHR and distribution teams in the field | Develop a proper training plan and curriculum, including materials, to expected audiences, from HQ - central (TOT) to health facilities and field personnel | Digitalization sub-committee
Digitalization implementation and setup according to DPoA and support | bar: 10 months before distribution W 3 to 4 months before distribution W4
35 | Set up helpdesk and support plan to manage incident and problems | Designate a staff member to manage | Digitalization sub-committee | bar: 10 months before distribution W 3 to 4 months before distribution W4
36 | Data management, dashboard key indicators and regular feedback to decision-makers | Digitalization will be implemented according to the campaign defined strategy (one time mass campaign vs. campaign in phases) and key indicators that will help develop the dashboard | Digitalization sub-committee | bar: 10 months before distribution W 3 to 4 months before distribution W4
37 | Helpdesk and issues escalation monitoring and troubleshooting | Helpdesk and support plan to manage incident and problems are in place with ICT4D staff and technical support at different levels | Digitalization sub-committee | bar: 10 months before distribution W 3 to 4 months before distribution W4
38 | Monitoring and supervision according to agreed SOPs | Close monitoring and supervision according to developed SOPs and unplanned issues | Digitalization sub-committee | bar: 10 months before distribution W 3 to 4 months before distribution W4
39 | Post digitalization activities | bar: 10 months before distribution W 3 to 4 months before distribution W4
| Digitalization devices reverse logistics | How to recover the devices that served during the digitalization | Digit support team/HMIS/Digit Partner | bar: 10 months before distribution W 3 to 2 months after distribution W4
40 | Backup of digitalization database | Ensure the databases and collected data are secured and well backed up | Digit support team/HMIS/Digit Partner | bar: 10 months before distribution W 3 to 2 months after distribution W4
41 | Lessons learned from the digitalization | Record the successes, failures and challenges of the campaign digitalization and lessons learned | Digit support team/HMIS/Digit Partner | bar: 10 months before distribution W 3 to 2 months after distribution W4
42 | Full inventory of digitalization equipment and devices | Exhaustive list of equipment, status and where to store them | Digit support team/HMIS/Digit Partner | bar: 10 months before distribution W 3 to 2 months after distribution W4
43
| Digitalization final report |  | Digit support team | bar: 10 months before distribution W 3 to 2 months after distribution W4
Activities associated with a direct cost (see generic budget)
Software and configuration
Based on the outcomes from the Campaign digitalization matrix and the components to be digitalized, propose and select platforms for the digitalization
A list of any other related software, hardware and infrastructure to set up
Configuration of servers (Cloud or on-premise infrastructure)
Technical support
Based on selected platforms and related software and hardware, identify expertise that will be needed for the digitalization plan and implementation
Develop a staffing plan and related ToRs (Digitalization HR plan)
Device and accessories
Ensure an accurate quantification for tablets, power bank and necessary accessories and start drafting a budget for the digitalization
Transportation and storage of devices
Liaise with Logistics to establish digitalization equipment storage and transport at different levels, HQ, provinces, districts etc.
Trainings and workshops
Digitalization training in cascade
Development of questionnaire and forms and digitalization into the selected platforms and devices according to campaign components to be digitalized
Convene regular sub-committee meetings with stakeholders