## BYOD risks
Adaptable tool - Table 6.
Key BYOD risk areas, priority and mitigation measures
Category | Risk area | Example risk | Mitigation measures
Technical | Device compatibility | Personal devices do not meet minimum app requirements | Define minimum device specifications; conduct device census and verification before roll-out; maintain a loaner device pool
Technical | Device performance | Low battery life, limited storage, app crashes, or poor GPS accuracy | Test app on common device types; require minimum RAM and storage; provide charging guidance or power banks where feasible
Technical | Technical support | Mixed device types create more support needs than expected | Set up tiered support arrangements; prepare troubleshooting guides; train supervisors to resolve basic issues
Technical | Platform stability | App or platform failure disrupts campaign implementation | Test the platform before roll-out; define escalation procedures; maintain vendor support and fallback arrangements
Operational | Connectivity and synchronization | Weak network coverage delays sync and affects real-time monitoring | Use offline-first applications; define sync points and sync schedules; provide supervisor monitoring for non-synced devices; plan paper or POD fallback where needed
Operational | Data quality | Inconsistent digital literacy or unfamiliar workflows lead to incomplete or inaccurate submissions | Provide practical, role-based training; simplify forms; use in-app validation and skip logic; strengthen supervisor review
Operational | Duplication and fraud | Multiple submissions for the same household or unauthorized entries | Use unique identifiers, duplicate checks, audit trails and supervisor review; apply server-side validation where possible
Operational | Incident reporting | Device loss, misuse or technical problems are not reported quickly enough | Establish a clear incident reporting process; train users and supervisors on escalation steps; share support contacts widely
Security | Data protection and privacy | Personal and campaign data coexist on the same device, increasing risk of unauthorized access or sharing | Use secure login, role-based access and encryption; restrict data export; require screen lock; provide clear acceptable use guidance
Security | Device loss or theft | A device containing campaign data is lost, stolen or replaced during implementation | Require immediate incident reporting; enable remote deactivation or data wipe where possible; limit local data storage; verify replacement devices before use
Security | Shared device use | Household members or other users access the campaign app or data on a shared phone | Require individual user accounts; prohibit account sharing; assess whether BYOD is suitable where private device use cannot be assured
Security | Unsafe device configuration | Rooted or jailbroken devices bypass security controls | Exclude rooted or jailbroken devices from BYOD participation; verify device status during enrolment
Security | Post-campaign data residue | Campaign data remain on personal devices after the campaign ends | Apply a closeout process; deactivate accounts; clear local data where required; conduct spot-checks where feasible
Security | Sensitive location data | GPS data expose households in conflict-affected or politically sensitive areas | Reduce GPS precision where needed; restrict export of location data; assess risk by zone before roll-out
Legal/governance | Governance and accountability | Unclear responsibility for device-related incidents, policy violations or non-compliance | Define user responsibilities, incident reporting pathways, and consequences for non-compliance in a simple BYOD policy
Legal/governance | Regulatory compliance | Personal device processing of household data is restricted by national law or authority | Review legal requirements early; conduct a Data Protection Impact Assessment (DPIA) where appropriate; engage relevant authorities; limit collection of personal data to the operational minimum
Legal/governance | High-risk functions | Sensitive activities such as bulk payments or system administration are performed on personal devices | Restrict high-risk functions to programme-owned, controlled devices
Equity/HR | Equity and inclusion | Some workers do not own suitable smartphones or prefer not to use personal devices | Make BYOD voluntary; provide programme-owned or loaner devices; use hybrid deployment where needed
Equity/HR | Coercion or unfair participation pressure | Workers feel compelled to use personal devices to remain eligible for work or payment | Separate BYOD participation from payment eligibility; provide opt-out options; communicate the policy clearly during training
Equity/HR | Policy comprehension | Workers do not fully understand BYOD conditions or responsibilities | Use plain language and local language forms; provide verbal briefing and comprehension checks during training
Financial/sustainability | Incentives and reimbursement | Workers incur data or charging costs and feel unfairly treated | Define clear compensation arrangements before roll-out; provide data bundles, stipends or other support
Financial/sustainability | Device replacement expectations | Workers expect the programme to replace damaged or lost personal devices | Define and communicate a clear policy on replacement, repair and compensation before implementation
Financial/sustainability | Long-term affordability | BYOD allowances used in one campaign are not sustainable in future campaigns | Set realistic support levels; document cost assumptions; align with longer-term programme budgeting
Reputational | Community trust | Communities become concerned about data misuse when campaign workers use personal phones | Conduct community sensitization; use clear consent scripts and privacy messages; monitor and respond to rumours quickly